## Sheet1
No | Nama Sumur | Nama Rig | Hari ke | Kedalaman (mMD) | Progress (mMD) | AFE | Realisasi Biaya | EMD | Summary Report | Current Status | Next Plan
1 | MDP-1x | ASIAN ENDEAVOUR-1 | 128 | 4738 | 4260 | 45414090 | 46230636 | 2026-01-27 | CONTINUE SEA FASTENING - JACK HULL DOWN - CONNECT MAIN TOW VESSEL - WATER TIGHT INTEGRITY TEST - FREE LEG OPERATION | FREE LEG OPERATION. | FREE LEG OPERATION.
2 | TASHA MOVE WPS-5 TO WPN-8 | TASHA | 9 | 0 |  |  | 1089683 |  | ATTEMPT TO RIG FINAL POSITIONING. | CONT' POSITIONING RIG. | FINAL RIG POSITIONING - PRELOAD ALL LEG.
3 | NB-702-bSH1 | Zhong You Hai – 16 | 37 | 4362 | 4348 | 22639078 | 13780779 | 2026-02-11 | PERFORATE ZONE #2 (4160-4164.5 mGR (4.5 m) - POOH & L/D TCP GUN ASSY - M/U 7" MST GP TRIP #1 FOR ZONE 2 - RIH 7" GP ASSY ON 3½" DP TO 901 mMD. | RIH 7" GP ASSY ON 3½" DP TO 3000 mMD. | SET PACKER - GP PUMPING ZONE #2 - POOH GP MST SERVICE TOOL.
4 | TN-S62 | RAISIS 102 | 21 | 4198 | 4196 | 6059059 | 5853516 | 2026-01-25 | RIG DEBALLASTING | OPERATION AT TN-D78. | OPERATION AT TN-D78.
5 | TN-D78 | RAISIS 102 | 1 | 1563 |  | 2374236 | 590982 | 2026-02-07 | WAIT ON TIDE - RIG MOVE OUT F/ TN-S60/61/62 TO TN-D78/79/80 - RIG POSITIONING. | SKID OUT RIG FLOOR. | SKID OUT RIG FLOOR - M/U TUBULARS - M/U CLEAN OUT BHA - CLEAN OUT CP.
6 | H-Y-472 | YANI RIG 104 | 2 | 4042 | 198 | 5425535 | 790320 | 2026-02-08 | N/U DIVERTER & BELL NIPPLE. COMPLETE ALL SHALLOW GAS CHECK LIST. M/U & RIH CP CLEAN OUT BHA. PERFORM CLEAN OUT CP. DROP GYRO. PUMP OOH CLEAN OUT CP BHA. M/U & RIH 12.25" MOTOR BHA TO 120 mMD. DRILL 12.25" HOLE F/ 120 TO 198 mMD/ 197.4 mTVD. | DRILL 12.25" HOLE AT 485 mMD/ 482 mTVD. | DRILL 12.25" HOLE TO SECTION TD AT 1250 mMD.