## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | GWDC-265 | PAS-001ST | PAS-001ST | Development | Onshore | [5 empty] | R/D H-4 : 75% |  | * R/D 100% - Rig Demobilization | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | * Wait on construction readiness for Location PCT-Y, Pasircatang. Est. M1 Jan 2026 (Progress: 96%) * Inspection CAT 3 (finding : Critical (16 item, 15 closed), major (61 item, 53 closed) and minor (17 item, 15 closed)) * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1 | * Wait on construction readiness for Location PCT-Y, Pasircatang. Est. M1 Jan 2026 (Progress: 96%) * Inspection CAT 3 (finding : Critical (16 item, 15 closed), major (61 item, 53 closed) and minor (17 item, 15 closed)) * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1 | * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1. * Continue Rig Premove | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | * Rig Idle (H-48). Rig Idle at Location CMR-STOB. * Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 14%) * Wait on AFE approved. | * Rig Idle (H-48). Rig Idle at Location CMR-STOB. * Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 14%) * Wait on AFE approved. | * Rig Idle. | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | RIH OE String to 1069 mMD, no cement - Circulation. - Pressure test casing, failed @ 200 psi - Remedial cement job #2. Loss rate 0.3 bpm with 300 gpm during reverse out. - WOC - RIH OE String to 906 mMD - Circulation conditioning MW - RIH OE String to tag TOC at 952 mMD | Circulation. Pressure test casing 300 psi drop to 0 psi - POOH OE string to 134 mMD | POOH OE string to surface - RIH 6" TCB + BHA Rotary to 952 - Drill out cement - Circulation | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | RIH 20" casing to 596 mMD - Circulation - Cement job 20" casing | Cement job 20" casing - WOC | WOC - N/D Diverter 29-1/2" - N/D BF 29-1/2" - N/U WH Sec A 20-3/4" | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | * Rig Idle (H-48), Rig Idle at Location BJR-D3. * Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 5%) | * Rig Idle (H-48), Rig Idle at Location BJR-D3. * Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 5%) | * Rig Idle. | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | CKR-STO2 | CKR-STO2 | Development | Onshore | [5 empty] | Rig Idle (H-4), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | * Rig Idle, inspection CAT III EXPLORATION | 2026-01-02 | 2026-01-01
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | N/U & Test RBOP 13-5/8" x 5K - S/U Tubular - RIH 8-1/2" PDC + BHA DD to 5 mMD | RIH 8-1/2" PDC + BHA DD to 33 mMD | RIH 8-1/2" PDC + BHA DD to TOC est at 901 mMD - Drill out cement and new formation to 934 mMD - Perform MOT 1.50 SG EMW - Drill 8-1/2" hole to 1463 mMD | 2026-01-02 | 2026-01-01