## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | Completed finding Inspection CAT 3 (finding : Critical (16 item, 16 closed), major (61 item, 61 closed) and minor (17 item, 17 closed)) - Premove (H-19) while Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1, kumm. 23% | Completed finding Inspection CAT 3 (finding : Critical (16 item, 16 closed), major (61 item, 61 closed) and minor (17 item, 17 closed)) - Premove (H-19) while Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1, kumm. 23% | Premoving Rig | 2026-01-09 | 2026-01-08
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-55). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 15%) - Wait on AFE approved. | Rig Idle (H-55). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 15%) - Wait on AFE approved. | Rig Idle. | 2026-01-09 | 2026-01-08
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | Drill out cement to 1056 mMD - Circulation - Pressure test to 250 psi - Hold - Drill out cement to 1251 mMD - Circulation - POOH 6" TCB + BHA rotary to 1011 mMD | POOH 6" TCB + BHA rotary to surface | M/U & RIH 7" + 9-5/8" tandem scrapper to 1251 mMD - Displace hole - POOH 7" + 9-5/8" tandem scrapper to surface | 2026-01-09 | 2026-01-08
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | Drill out cement and 2 meter new formation to 600 mMD - Circulation - Perform MOT with 1.37 EMW - POOH 17-1/2" TCB + BHA rotary to 504 mMD | POOH 17-1/2" TCB + BHA Rotary to 107 mMD | POOH 17-1/2" TCB + Rotary BHA to surface - M/U & RIH 18-1/2" PDC + BHA DD to 600 mMD - Drill 18-1/2" hole to 1041 mMD | 2026-01-09 | 2026-01-08
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-54), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-54), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle. | 2026-01-09 | 2026-01-08
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | CKR-STO2 | CKR-STO2 | Development | Onshore | [5 empty] | Rig Idle (H-11), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | Rig Idle, inspection CAT III | 2026-01-09 | 2026-01-08
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | RIH 1-11/16" dummy puncher to 1371 mMD - POOH 1-11/16" dummy puncher to surface - RIH 1-11/16" gun puncher to 1371 mMD - Correlation & set puncher at 1368 mMD - Shooting gun puncher - got indication fired - POOH 1-11/16" gun puncher to surface - R/D Wireline - Attempt to circulation several time with various pressure - no succeed - R/U wireline - RIH 1-11/16" gun puncher #2 to 801 mMD - Correlation & set puncher at 801 mMD - Shooting gun puncher - got indication fired - POOH 1-11/16" gun puncher to surface - R/D Wireline - Attempt to circulation several time with various pressure - no succeed - POOH RT LH to 428 mMD | POOH RT LH to surface - R/D RBOP, on progress | R/D RBOP - RIH & set 7" RTTS packer to 30 meter below perforated #2 - Circulation | 2026-01-09 | 2026-01-08