## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | Rig Move to PCT-Y (H-2), kumm. 39% | Rig Move to PCT-Y (H-2), kumm. 39% | Rig Move 100% | 2026-01-10 | 2026-01-09
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | KRE-002ST | KRE-002ST | Development | Onshore | [5 empty] | Rig Idle (H-55). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) | Rig Idle (H-55). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) | Rig Idle. | 2026-01-10 | 2026-01-09
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | POOH 6" TCB + BHA rotary to surface - RIH 7" + 9-5/8" scrapper tandem to 1251 mMD - Displace hole with 1.36 SG CF CaCl2 Brine - POOH 7" + 9-5/8" Scrapper tandem to surface - R/U wireline | Perform CH logging : CBL-CAST interval 940-1240 mMD | RIH production string 2-7/8" tubing + TCP assy to 1051 mMD - Correlation TCP | 2026-01-10 | 2026-01-09
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | POOH 17-1/2" TCB + BHA rotary to surface - RIH 18-1/2" PDC + BHA directional to 559 mMD | RIH 18-1/2" PDC + BHA directional to 593 mMD | RIH 18-1/2" PDC + BHA DD to 600 mMD - Drill 18-1/2" hole to 1041 mMD | 2026-01-10 | 2026-01-09
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-55), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-55), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle, inspection CAT III | 2026-01-10 | 2026-01-09
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-12), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval |  |  | 2026-01-10 | 2026-01-09
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | POOH RT LH to surface - R/D RBOP - RIH & set 7" RTTS packer BHA to 836 mMD - Attempt to circulation with various pressure - negative | unset & POOH 7" RTTS packer BHA to 100 mMD | POOH 7" RTTS packer BHA to surface - R/U PCE - Perforation job between puncher #1 & puncher#2 depth - RIH & set 7" packer BHA | 2026-01-10 | 2026-01-09