## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | Rig Move to PCT-Y (H-5), kumm. 76% | Rig Move to PCT-Y (H-5), kumm. 76% | Rig Move 100% | 2026-01-13 | 2026-01-12
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | KRE-002ST | KRE-002ST | Development | Onshore | [5 empty] | Rig Idle (H-58). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) | Rig Idle (H-58). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) | Rig Idle. | 2026-01-13 | 2026-01-12
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | N/D BOP 13-5/8" x 5000 psi - N/U x-mastree - R/U CTU - Unload water cushion - Drop bar, fired indication. - Closed observation Pwh/Pcsg/Pfl : 0 psi/500 psi/0 psi - Unload job : Sample oil contamination | Closed observation Pwh/Pcsg : 230-330 psi/500-250 psi | Closed observation - Clean out well - Production test | 2026-01-13 | 2026-01-12
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | Drill 18-1/2" hole section to 1008 mMD/991.7 mTVD (CP 16” Confirmed by WSG) - Circulation - POOH 18-1/2" PDC + BHA DD to 501 mMD - Circulation - RIH 18-1/2" PDC + BHA DD to 601, attempt to RIH deeper not succeed. | POOH 18-1/2" PDC + BHA DD to 530 mMD | RIH 18-1/2" PDC + BHA DD to bottom 1008 mMD - Circulation - POOH 18-1/2" PDC + BHA DD to surface | 2026-01-13 | 2026-01-12
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-58), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-58), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle, inspection CAT III | 2026-01-13 | 2026-01-12
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-15), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval |  |  | 2026-01-13 | 2026-01-12
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | R/U wireline - RIH & Shoot puncher #4 interval 805-806 mMD - R/D Wireline - RIH 7" RTTS packer BHA to 760 mMD - Set RTTS - Communication test reverse circulation, gradually stable return at 100 gpm. - Comminication test straight circulation, not succeed. | Communication test straight circulation, not succeed. | Communication test | 2026-01-13 | 2026-01-12