## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | Rig Move to PCT-Y (H-6), kumm. 88% | Rig Move to PCT-Y (H-6), kumm. 88% | Rig Move 100% | 2026-01-14 | 2026-01-13
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | KRE-002ST | KRE-002ST | Development | Onshore | [5 empty] | Rig Idle (H-59). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle (H-59). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle. | 2026-01-14 | 2026-01-13
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | Closed observation Pwh/Pcsg : 230-330 psi/500-250 psi - R/U Injector head CTU - Unload Job #2 : Vol Total/ SG/ pH/ Cl-/ (151.9 Bbl/ 0.94/ -/ 12-13k/Fluid sample) - POOH CT to surface. - Closed observation : Pwh/Pcsg : 260-450 psi/500-100 psi | Closed observation : Pwh/Pcsg : 260-450 psi/500-100 psi | Acidizing job - Unload job - Clean out well - Production test | 2026-01-14 | 2026-01-13
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | POOH 18-1/2" PDC + BHA DD to 509 mMD while checkshot, accidentally sidetrack indication - RIH 18-1/2" PDC + BHA DD to 601 mMD with orienting desired GTF, attempt to RIH deeper not succeed. - POOH 18-1/2" PDC + BHA DD to 15 mMD | POOH 18-1/2" PDC + BHA DD to surface - RIH 17-1/2" TCB + BHA Rotary to 95 mMD | RIH 17-1/2" TCB + BHA Rotary to 1008 mMD - Circulation - POOH 17-1/2" TCB + BHA Rotary to 95 mMD | 2026-01-14 | 2026-01-13
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-59), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-59), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle, inspection CAT III | 2026-01-14 | 2026-01-13
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-16), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval - Wait on FID est March 2026 |  |  | 2026-01-14 | 2026-01-13
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | Communication test straight circulation, not succeed. - Unset RTTS - POOH RTTS BHA to 731 mMD - Cut and slip drilling line - POOH RTTS BHA to surface - RIH OE 2-7/8" Tubing + DP to 768 mMD | RIH OE 2-7/8" Tubing + DP to 1370 mMD | Cementing Squeeze job #1 interval 1306-1368 mMD - WOC - RIH OE to tag TOC - Cementing Squeeze job #2 interval 801-806 mMD | 2026-01-14 | 2026-01-13