## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | Rig Move to PCT-Y (H-7), kumm. 93% | Rig Move to PCT-Y (H-7), kumm. 93% | Rig Move 100% | 2026-01-15 | 2026-01-14
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | KRE-002ST | KRE-002ST | Development | Onshore | [5 empty] | Rig Idle (H-60). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle (H-60). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle. | 2026-01-15 | 2026-01-14
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | Closed observation : Pwh/Pcsg : 260-450 psi/500-100 psi - Acidizing job - Unload job - Unload job #3 (Vol Total/ SG/ pH/ Cl-/ Description:64.3 Bbl/0.84/ -/ -/Sample fluid) - POOH CTU to surface - Closed observation Pwh/Pcsg : 120-240 psi/200-20 psi | Closed observation Pwh/Pcsg : 120-240 psi/200-20 psi | Unload job #4 - Production test - Rig Release | 2026-01-15 | 2026-01-14
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | POOH 18-1/2" PDC + BHA DD to surface - RIH 17-1/2" TCB + BHA Rotary to 602 mMD, attempt to RIH deeper not succeed. - POOH 17-1/2" TCB + BHA Rotary to surface - RIH OE DP to 534 mMD, attempt to RIH deeper not succeed. - POOH OE DP to surface ⦁ RIH 6" TCB + BHA to 58 mMD | ⦁ RIH 6" TCB + BHA to 532 mMD, attempt to RIH deeper not succeed. | ⦁ POOH 6" TCB + BHA to surface ⦁ RIH 8-1/2" TCB + BHA to 600 mMD - Circulation - Plug back cement job - WOC - RIH 8-1/2" TCB + BHA to tag TOC - POOH 8-1/2" TCB + BHA to surface | 2026-01-15 | 2026-01-14
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-60), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-60), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle, inspection CAT III | 2026-01-15 | 2026-01-14
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-17), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval - Wait on FID est March 2026 |  |  | 2026-01-15 | 2026-01-14
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | RIH OE 2-7/8" Tubing + DP to 1370 mMD - Cementing Squeeze job #1 interval 1306-1368 mMD - WOC - RIH OE to 1189 mMD, tagged TOC ⦁ Circulation | Cementing Squeeze job #2 interval 801-806 mMD | WOC - RIH OE to tag TOC - POOH OE to surface | 2026-01-15 | 2026-01-14