## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | Rig Move to PCT-Y (H-7), kumm.100 % - R/U (H-1) : 18% | Rig Move to PCT-Y (H-7), kumm.100 % - R/U (H-1) : 18% | R/U 100% | 2026-01-16 | 2026-01-15
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | KRE-002ST | KRE-002ST | Development | Onshore | [5 empty] | Rig Idle (H-61). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle (H-61). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle. | 2026-01-16 | 2026-01-15
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | Closed observation Pwh/Pcsg : 120-240 psi/200-20 psi - Production test (Ptbg / Pcsg / Pfl / Psep / Qgas / Gross, BLPD / Nett, BOPD / WC% / Bean : 95 psi / 0 psi / 20 psi / 14 psi / 96.331 MSCFD / 330 blpd / 186 bopd / 47.4% / 7 mm). - Rig PDSI #12.3/N110-M dinyatakan Released TMT Kamis, 15 Januari 2026 pukul 16.00 WIB dan Sumur BDA-008 (BDA-D1) dinyatakan sebagai sumur penghasil Hydrocarbon dari Layer C1 Interval 1044.83-1050.83 mMD ⦁ R/D (H-1): 8% | ⦁ R/D (H-1) : 13% | R/D 100% | 2026-01-16 | 2026-01-15
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | RIH 6" TCB + BHA to 532 mMD, attempt to RIH deeper not succeed. - POOH 6" TCB + BHA to surface - RIH 8-1/2" TCB + BHA Rotary to 602 mMD - Circulation - Kick off cement plug ⦁ WOC | RIH 8-1/2" TCB + BHA to 484 mMD, tagged TOC - POOH 8-1/2" TCB + BHA to 300 mMD | POOH 8-1/2" TCB + BHA to surface - RIH 17-1/2” TCB + BHA Rotary to TOC - DOC to 530 mMD - Circulation - POOH 17-1/2” TCB + BHA Rotary to surface - M/U & RIH 18-1/2" Milling Assy to 521 mMD - Dress out interval 521 - 530 mMD - POOH 18-1/2" Milling assy to surface | 2026-01-16 | 2026-01-15
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-61), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-61), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle, inspection CAT III | 2026-01-16 | 2026-01-15
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-18), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval - Wait on FID est March 2026 |  |  | 2026-01-16 | 2026-01-15
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | Cementing Squeeze job #2 interval 801-806 mMD - WOC - RIH OE to 834 mMD - P/T casing, drop from 703 psi to 498 psi - RIH EO to 914 mMD - Cementing Squeeze job #3 interval 801-806 mMD | WOC | WOC - RIH OE to tag TOC - POOH OE to surface | 2026-01-16 | 2026-01-15