## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary | Current Status | Next Plan | Report Date | Operation Date
INC | Region 2 | Zone 7 | PEP | PDSI #04.3/N110-M | PCT-Y | PCT-Y | Development | Onshore | [5 empty] | R/U (H-3) : 31% | R/U (H-3) : 31% | R/U 100% | 2026-01-18 | 2026-01-17
INC | Region 2 | Zone 7 | PEP | PDSI #09.2/N80UE | KRE-002ST | KRE-002ST | Development | Onshore | [5 empty] | Rig Idle (H-63). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle (H-63). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | Rig Idle. | 2026-01-18 | 2026-01-17
INC | Region 2 | Zone 7 | PEP | PDSI #12.3/N110-M | BDA-008 | BDA-008 | Development | Onshore | [5 empty] | R/D (H-3): 58% |  | R/D 100% | 2026-01-18 | 2026-01-17
INC | Region 2 | Zone 7 | PEP | PDSI #15.3/N110-M | BMH-002 | BMH-002 | Development | Onshore | [5 empty] | DOC to 525 mMD, no drilling progress. - Circulation - POOH 17-1/2” TCB + BHA Rotary to surface - M/U & RIH 17-1/2" Milling Assy to 525 mMD - Perform milling 17-1/2" to 530 mMD | Perform milling 17-1/2" to 533 mMD | Dress out interval 525-537 mMD - POOH 17-1/2" Milling assy to surface | 2026-01-18 | 2026-01-17
INC | Region 2 | Zone 7 | PEP | PDSI #28.2/D1000-E | TGP-INF1 | TGP-INF1 | Development | Onshore | [5 empty] | Rig Idle (H-63), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle (H-63), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | Rig Idle, inspection CAT III | 2026-01-18 | 2026-01-17
INC | Region 2 | Zone 7 | PEP | PDSI #31.3/D1500-E | AMJ-B1 | AMJ-B1 | Development | Onshore | [5 empty] | Rig Idle (H-20), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on FID est March 2026 |  |  | 2026-01-18 | 2026-01-17
INC | Region 2 | Zone 7 | PEP | WBR-01 | AMJ-004 | AMJ-004 | Development | Onshore | [5 empty] | WOC - RIH OE to 639 mMD, TOC tagged. - Circulation - POOH OE to surface - RIH 8-1/2" TCB + BHA Rotary to 639 mMD - DOC to 679 mMD | DOC to 718 mMD | DOC to 768 mMD - Circulation - POOH 8-1/2" TCB + BHA Rotary to surface - M/U 6" TCB BHA + Rotary to 768 mMD, DOC to 1397 mMD. | 2026-01-18 | 2026-01-17