## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / Heru S. / Raditya F. | 32 | 1,278m MD/1,277 mTVD | - RIH OE String to 1069 mMD, no cement - Circulation. - Pressure test casing, failed @ 200 psi - Remedial cement job #2. Loss rate 0.3 bpm with 300 gpm during reverse out. - WOC - RIH OE String to 906 mMD - Circulation conditioning MW - RIH OE String to tag TOC at 952 mMD | - Circulation. Pressure test casing 300 psi drop to 0 psi - POOH OE string to 134 mMD | - POOH OE string to surface - RIH 6" TCB + BHA Rotary to 952 - Drill out cement - Circulation
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Ganang W.S / A. Fatah / Harry F Sani | 13 | 931 mMD/880.39 mTVD | - N/U & Test RBOP 13-5/8" x 5K - S/U Tubular - RIH 8-1/2" PDC + BHA DD to 5 mMD | - RIH 8-1/2" PDC + BHA DD to 33 mMD | - RIH 8-1/2" PDC + BHA DD to TOC est at 901 mMD - Drill out cement and new formation to 934 mMD - Perform MOT 1.50 SG EMW - Drill 8-1/2" hole to 1463 mMD
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | - |  |  |  | * Wait on construction readiness for Location PCT-Y, Pasircatang. Est. M1 Jan 2026 (Progress: 96%) * Inspection CAT 3 (finding : Critical (16 item, 15 closed), major (61 item, 53 closed) and minor (17 item, 15 closed)) * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1 | * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1. * Continue Rig Premove
JATIBARANG | AMJ-B1 |  | PDSI #09.2/N80UE | - |  |  |  | * Rig Idle (H-48). Rig Idle at Location CMR-STOB. * Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 14%) * Wait on AFE approved. | * Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Nurdiansyah/Herry Prabowo/Gilang Rizki K | 5 | 598 mMD/596.75 mTVD | - RIH 20" casing to 596 mMD - Circulation - Cement job 20" casing | - Cement job 20" casing - WOC | - WOC - N/D Diverter 29-1/2" - N/D BF 29-1/2" - N/U WH Sec A 20-3/4"
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | * Rig Idle (H-48), Rig Idle at Location BJR-D3. * Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 5%) | * Rig Idle.
TAMBUN | CKR-STO2 | CKR-STO2 | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-4), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | * Rig Idle, inspection CAT III EXPLORATION
TAMBUN | PAS-001ST | PAS-001 | GWDC-265 | Mimbar H |  |  | - R/D H-4 : 75% |  | * R/D 100% - Rig Demobilization