## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / Heru S. / Raditya F./ M. Reyhan W. | 34 | 1,278m MD/1,277 mTVD | - Circulation. Pressure test casing 300 psi drop to 0 psi - POOH OE string to surface - RIH 6" TCB + BHA Rotary to 952 - Drill out cement to 960 mMD - RIH washdown to 960-1128 mMD - Circulation. - POOH 6" TCB + BHA Rotary to surface - RIH OE string to 822 mMD - Remedial cement job #3 with superflush & gas tight slurry - WOC | - RIH OE string to 1024 mMD, no cement tag | - Circulation - Remedial cement job #4 - WOC - RIH OE string to tag TOC - Circulation - POOH OE string to surface
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | A. Fatah / Harry F Sani | 15 | 1311 mMD/ 1229.4 mTVD | - Drill 8-1/2" hole to 1311 mMD | - Drill 8-1/2" hole to 1368 mMD | - Drill 8-1/2" hole to 1463 mMD (est TD well) - Circulation - POOH 8-1/2" PDC + BHA DD to surface
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | - |  |  |  | * Wait on construction readiness for Location PCT-Y, Pasircatang. Est. M1 Jan 2026 (Progress: 96%) * Inspection CAT 3 (finding : Critical (16 item, 15 closed), major (61 item, 60 closed) and minor (17 item, 16 closed)) - Lifting gear inspection (65%) * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1 | * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1. * Continue Rig Premove
JATIBARANG | AMJ-B1 |  | PDSI #09.2/N80UE | - |  |  |  | * Rig Idle (H-50). Rig Idle at Location CMR-STOB. * Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 14%) * Wait on AFE approved. | * Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Herry Prabowo/Gilang Rizki K/Taufik Adi P | 7 | 598 mMD/596.75 mTVD | - Top Job #1 cement annulus casing 20" x 30" - WOC - No tag TOC to 80 mMD - Top Job #2 cement annulus casing 20" x 30", no cement return - WOC | - Top Job #3 cement annulus casing 20" x 30" - WOC | - WOC - N/D Diverter 29-1/2" - N/D BF 29-1/2" - N/U WH Sec A 20-3/4"
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | * Rig Idle (H-50), Rig Idle at Location BJR-D3. * Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 5%) | * Rig Idle.
TAMBUN | CKR-STO2 | CKR-STO2 | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-6), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | * Rig Idle, inspection CAT III