## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / Raditya F./ M. Reyhan W. | 36 | 1,278m MD/1,277 mTVD | * WOC * RIH OE BHA to tag TOC at 943 mMD * Circulation * POOH OE BHA to surface * RIH 6" TCB + BHA Rotary to 943 mMD * P/test casing to 500 psi - ok. * Drill out cement to 983 mMD | * Drill out xement to 1021 mMD | * Drill out cement to 1055 mMD * p/test casing * Continue drill out cement to tag LC at 1251 mMD * Circulation * POOH 6" TCB + BHA Rotary to surface * RIH 7" scrapper to 1251 mMD
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | A. Fatah / Harry F Sani / Abdurrahman | 17 | 1462 mMD/ 1366 mTVD | * POOH 8-1/2" PDC + BHA DD to surface * R/U Wireline * Perform 8-1/2" OH Logging : GR-JAR-RDT-FLIP-MCS, completed 20 points * R/D Wireline | - RIH 7" Liner (L80-13Cr, 26 ppf, VAM21, R3 + R2) to 85 mMD | * RIH 7" Liner (L80-13Cr, 26 ppf, VAM21, R3 + R2) + 7" x 9-5/8" Hyd Rotatable Liner Hanger to 1460 mMD * Cementing Job 7" Liner
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | - |  |  |  | * Inspection CAT 3 (finding : Critical (16 item, 15 closed), major (61 item, 60 closed) and minor (17 item, 16 closed)) * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1 | * Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1. * Rig Moving
JATIBARANG | AMJ-B1 |  | PDSI #09.2/N80UE | - |  |  |  | * Rig Idle (H-52). Rig Idle at Location CMR-STOB. * Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 15%) * Wait on AFE approved. | * Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Herry Prabowo/Gilang Rizki K/Taufik Adi P | 9 | 598 mMD/596.75 mTVD | * N/U WH Sec A 20-3/4" x 3K * N/U BOP 21-1/4" x 2K | * N/U BOP 21-1/4" x 2K psi, on progress | * Test BOP 21-1/4" x 2K * RIH 18-1/2" PDC + Rotary BHA to tag FC * Drill out plugs, cement, shoe and 3 meter new formation to 601 mMD * Circulation * Perform MOT with 1.4 sg EMW * POOH 18-1/2" PDC + Rotary BHA to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | * Rig Idle (H-52), Rig Idle at Location BJR-D3. * Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | * Rig Idle.
TAMBUN | CKR-STO2 | CKR-STO2 | PDSI #31.3/D1500-E | - |  |  | * Rig Idle (H-8), Rig idle at location ABG-H4 while Inpection Rig Category III * Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | * Rig Idle, inspection CAT III