## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / M. Reyhan W. / Donny Y. | 38 | 1,278m MD/1,277 mTVD | - Perform remedial cementing #5 and hesitation with total volume 0.5 bbl - WOC - RIH OE BHA to tag TOC at 929 mMD - Circulation - POOH OE BHA to surface - RIH 6" TCB + rotary BHA to 929 mMD - Drill out cement to 945 mMD | - Drill out cement to 983 mMD | - Drill out cement to 1056 mMD - Pressure test casing - Drill out cement to 1251 mMD - Circulation
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | A. Fatah / Harry F Sani / Abdurrahman | 19 | 1462 mMD/ 1367 mTVD | - Attempt to free casing with WOP 30-420 klbs and Torque to 18 klbs.ft - not succeed. - Set 7" x 9-5/8" liner hanger & release R/T - R/U wireline | - RIH 1-11/16" dummy puncher to 50 WLM | - RIH dummy 1-11/16" puncher to tag LC. POOH - RIH 1-11/16" puncher to 3 meter above LC - Perform perforated casing 7" - POOH 1-11/16" puncher to surface - Circulation
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | - |  |  |  | - Inspection CAT 3 (finding : Critical (16 item, 15 closed), major (61 item, 61 closed) and minor (17 item, 17 closed)) - Continue Premove (H-19) while Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1, kumm. 16% | - Premoving while Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1.
JATIBARANG | AMJ-B1 |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-54). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 15%) - Wait on AFE approved. | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Herry Prabowo/Gilang Rizki K/Taufik Adi P | 11 | 598 mMD/596.75 mTVD | - Run 18-1/2" PDC + BHA Rotary to tag TOC at 362 mMD - Circulation - Drill out cement to 521 mMD, got eratiq torgue. - Circulation - POOH 18-1/2" PDC + Rotary BHA to surface - RIH 17-1/2" TCB + BHA Rotary to 521 mMD - Drill out cement to 522 mMD | - Drill out cement to 526 mMD | - Drill out plugs, cement, shoe and 2 meter new formation to 600 mMD - Circulation - Perform MOT with 1.4 sg EMW - POOH 17-1/2" TCB + Rotary BHA to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-53), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle.
TAMBUN | CKR-STO2 | CKR-STO2 | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-10), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | - Rig Idle, inspection CAT III