## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / M. Reyhan W. / Donny Y. | 39 | 1,278m MD/1,277 mTVD | - Drill out cement to 1056 mMD - Circulation - Pressure test to 250 psi - Hold - Drill out cement to 1251 mMD - Circulation - POOH 6" TCB + BHA rotary to 1011 mMD | - POOH 6" TCB + BHA rotary to surface | - M/U & RIH 7" + 9-5/8" tandem scrapper to 1251 mMD - Displace hole - POOH 7" + 9-5/8" tandem scrapper to surface
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | A. Fatah / Harry F Sani / Abdurrahman | 20 | 1462 mMD/ 1367 mTVD | - RIH 1-11/16" dummy puncher to 1371 mMD - POOH 1-11/16" dummy puncher to surface - RIH 1-11/16" gun puncher to 1371 mMD - Correlation & set puncher at 1368 mMD - Shooting gun puncher - got indication fired - POOH 1-11/16" gun puncher to surface - R/D Wireline - Attempt to circulation several time with various pressure - no succeed - R/U wireline - RIH 1-11/16" gun puncher #2 to 801 mMD - Correlation & set puncher at 801 mMD - Shooting gun puncher - got indication fired - POOH 1-11/16" gun puncher to surface - R/D Wireline - Attempt to circulation several time with various pressure - no succeed - POOH RT LH to 428 mMD | - POOH RT LH to surface - R/D RBOP, on progress | - R/D RBOP - RIH & set 7" RTTS packer to 30 meter below perforated #2 - Circulation
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | - |  |  |  | - Completed finding Inspection CAT 3 (finding : Critical (16 item, 16 closed), major (61 item, 61 closed) and minor (17 item, 17 closed)) - Premove (H-19) while Closing finding as a Memo no. 092/PHE20000/2025/S0 & No.1982/PEP82210/2025-S1, kumm. 23% | - Premoving Rig
JATIBARANG | AMJ-B1 |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-55). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location AMJ-B1. Est M2 Feb 2026 (Progress: 15%) - Wait on AFE approved. | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Herry Prabowo/Gilang Rizki K/Taufik Adi P | 12 | 598 mMD/596.75 mTVD | - Drill out cement and 2 meter new formation to 600 mMD - Circulation - Perform MOT with 1.37 EMW - POOH 17-1/2" TCB + BHA rotary to 504 mMD | - POOH 17-1/2" TCB + BHA Rotary to 107 mMD | - POOH 17-1/2" TCB + Rotary BHA to surface - M/U & RIH 18-1/2" PDC + BHA DD to 600 mMD - Drill 18-1/2" hole to 1041 mMD
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-54), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle.
TAMBUN | CKR-STO2 | CKR-STO2 | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-11), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location CKR-STO2 (progress : 33%), est. Ready on M4 February 2026 |  | - Rig Idle, inspection CAT III