## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / M. Reyhan W. / Donny Y. | 40 | 1,278m MD/1,277 mTVD | - POOH 6" TCB + BHA rotary to surface - RIH 7" + 9-5/8" scrapper tandem to 1251 mMD - Displace hole with 1.36 SG CF CaCl2 Brine - POOH 7" + 9-5/8" Scrapper tandem to surface - R/U wireline | - Perform CH logging : CBL-CAST interval 940-1240 mMD | - RIH production string 2-7/8" tubing + TCP assy to 1051 mMD - Correlation TCP
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | A. Fatah / Harry F Sani / Abdurrahman | 21 | 1462 mMD/ 1367 mTVD | - POOH RT LH to surface - R/D RBOP - RIH & set 7" RTTS packer BHA to 836 mMD - Attempt to circulation with various pressure - negative | - unset & POOH 7" RTTS packer BHA to 100 mMD | - POOH 7" RTTS packer BHA to surface - R/U PCE - Perforation job between puncher #1 & puncher#2 depth - RIH & set 7" packer BHA
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | - |  |  |  | - Rig Move to PCT-Y (H-2), kumm. 39% | - Rig Move 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-12), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-55). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Gilang Rizki K/Taufik Adi P/Ari Welas | 13 | 600 mMD/598.05 mTVD | - POOH 17-1/2" TCB + BHA rotary to surface - RIH 18-1/2" PDC + BHA directional to 559 mMD | - RIH 18-1/2" PDC + BHA directional to 593 mMD | - RIH 18-1/2" PDC + BHA DD to 600 mMD - Drill 18-1/2" hole to 1041 mMD
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-55), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III