## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Wahyu Berbudi / M. Reyhan W. / Donny Y. | 43 | 1,278m MD/1,277 mTVD | - N/D BOP 13-5/8" x 5000 psi - N/U x-mastree - R/U CTU - Unload water cushion - Drop bar, fired indication. - Closed observation Pwh/Pcsg/Pfl : 0 psi/500 psi/0 psi - Unload job : Sample oil contamination | - Closed observation Pwh/Pcsg : 230-330 psi/500-250 psi | - Closed observation - Clean out well - Production test
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Harry F. Sani / Abdurrahman Malik / Ade Rama | 24 | 1462 mMD/ 1367 mTVD | - R/U wireline - RIH & Shoot puncher #4 interval 805-806 mMD - R/D Wireline - RIH 7" RTTS packer BHA to 760 mMD - Set RTTS - Communication test reverse circulation, gradually stable return at 100 gpm. - Comminication test straight circulation, not succeed. | - Communication test straight circulation, not succeed. | - Communication test
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | Haryo Abiyoso |  |  |  | - Rig Move to PCT-Y (H-5), kumm. 76% | - Rig Move 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-15), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-58). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Taufik Adi P/Ari Welas/Darwis YB | 16 | 1008 mMD/991.7 | - Drill 18-1/2" hole section to 1008 mMD/991.7 mTVD (CP 16” Confirmed by WSG) - Circulation - POOH 18-1/2" PDC + BHA DD to 501 mMD - Circulation - RIH 18-1/2" PDC + BHA DD to 601, attempt to RIH deeper not succeed. | - POOH 18-1/2" PDC + BHA DD to 530 mMD | - RIH 18-1/2" PDC + BHA DD to bottom 1008 mMD - Circulation - POOH 18-1/2" PDC + BHA DD to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-58), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III