## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | M. Reyhan W. / Donny Y. | 44 | 1,278 mMD/1,277 mTVD | - Closed observation Pwh/Pcsg : 230-330 psi/500-250 psi - R/U Injector head CTU - Unload Job #2 : Vol Total/ SG/ pH/ Cl-/ (151.9 Bbl/ 0.94/ -/ 12-13k/Fluid sample) - POOH CT to surface. - Closed observation : Pwh/Pcsg : 260-450 psi/500-100 psi | - Closed observation : Pwh/Pcsg : 260-450 psi/500-100 psi | - Acidizing job - Unload job - Clean out well - Production test
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Abdurrahman Malik / Ade Rama / Heru Sulistyo | 25 | 1462 mMD/ 1367 mTVD | - Communication test straight circulation, not succeed. - Unset RTTS - POOH RTTS BHA to 731 mMD - Cut and slip drilling line - POOH RTTS BHA to surface - RIH OE 2-7/8" Tubing + DP to 768 mMD | - RIH OE 2-7/8" Tubing + DP to 1370 mMD | - Cementing Squeeze job #1 interval 1306-1368 mMD - WOC - RIH OE to tag TOC - Cementing Squeeze job #2 interval 801-806 mMD
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | Haryo Abiyoso |  |  |  | - Rig Move to PCT-Y (H-6), kumm. 88% | - Rig Move 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-16), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval - Wait on FID est March 2026
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-59). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Taufik Adi P/Ari Welas/Darwis YB | 17 | 1008 mMD/991.7 mTVD | - POOH 18-1/2" PDC + BHA DD to 509 mMD while checkshot, accidentally sidetrack indication - RIH 18-1/2" PDC + BHA DD to 601 mMD with orienting desired GTF, attempt to RIH deeper not succeed. - POOH 18-1/2" PDC + BHA DD to 15 mMD | - POOH 18-1/2" PDC + BHA DD to surface - RIH 17-1/2" TCB + BHA Rotary to 95 mMD | - RIH 17-1/2" TCB + BHA Rotary to 1008 mMD - Circulation - POOH 17-1/2" TCB + BHA Rotary to 95 mMD
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-59), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III