## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | M. Reyhan W. / Donny Y. | 45 | 1,278 mMD/1,277 mTVD | - Closed observation : Pwh/Pcsg : 260-450 psi/500-100 psi - Acidizing job - Unload job - Unload job #3 (Vol Total/ SG/ pH/ Cl-/ Description:64.3 Bbl/0.84/ -/ -/Sample fluid) - POOH CTU to surface - Closed observation Pwh/Pcsg : 120-240 psi/200-20 psi | - Closed observation Pwh/Pcsg : 120-240 psi/200-20 psi | - Unload job #4 - Production test - Rig Release
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Abdurrahman Malik / Ade Rama / Heru Sulistyo | 26 | 1462 mMD/ 1367 mTVD | - RIH OE 2-7/8" Tubing + DP to 1370 mMD - Cementing Squeeze job #1 interval 1306-1368 mMD - WOC - RIH OE to 1189 mMD, tagged TOC ⦁ Circulation | - Cementing Squeeze job #2 interval 801-806 mMD | - WOC - RIH OE to tag TOC - POOH OE to surface
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | Haryo Abiyoso |  |  |  | - Rig Move to PCT-Y (H-7), kumm. 93% | - Rig Move 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-17), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval - Wait on FID est March 2026
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-60). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Taufik Adi P/Ari Welas/Darwis YB | 18 | 1008 mMD/991.7 mTVD | - POOH 18-1/2" PDC + BHA DD to surface - RIH 17-1/2" TCB + BHA Rotary to 602 mMD, attempt to RIH deeper not succeed. - POOH 17-1/2" TCB + BHA Rotary to surface - RIH OE DP to 534 mMD, attempt to RIH deeper not succeed. - POOH OE DP to surface ⦁ RIH 6" TCB + BHA to 58 mMD | ⦁ RIH 6" TCB + BHA to 532 mMD, attempt to RIH deeper not succeed. | ⦁ POOH 6" TCB + BHA to surface ⦁ RIH 8-1/2" TCB + BHA to 600 mMD - Circulation - Plug back cement job - WOC - RIH 8-1/2" TCB + BHA to tag TOC - POOH 8-1/2" TCB + BHA to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-60), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III