## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Abdurrahman Malik / Ade Rama / Heru Sulistyo | 28 | 1462 mMD/ 1367 mTVD | - WOC - RIH OE to 814 mMD, no TOC tagged. - P/T casing 600 psi drop to 470 psi. - RIH OE to 1008 mMD - Circulation - POOH OE to 833 mMD - Squeeze Cement Block #4 interval 801-806 mMD - WOC | - WOC | - WOC - RIH OE to tag TOC - POOH OE to surface
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | Haryo Abiyoso |  |  |  | - R/U (H-2) : 26% | - R/U 100%
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | M. Reyhan W. / Donny Y. |  |  | - R/D (H-2): 33% |  | - R/D 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-19), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on AFE approval - Wait on FID est March 2026
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-62). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Ari Welas/Darwis YB/M.Feisal | 20 | 1008 mMD/991.7 mTVD | - RIH 8-1/2" TCB + BHA to 484 mMD, tagged TOC - POOH 8-1/2" TCB + BHA to surface - RIH 17-1/2” TCB + BHA Rotary to 482 mMD - DOC to 520 mMD | - DOC to 524 mMD | - DOC to 537 mMD - Circulation - POOH 17-1/2” TCB + BHA Rotary to surface - M/U & RIH 18-1/2" Milling Assy to 521 mMD - Dress out interval 521 - 530 mMD - POOH 18-1/2" Milling assy to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-62), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III