## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Abdurrahman Malik / Ade Rama / Heru Sulistyo | 29 | 1462 mMD/ 1367 mTVD | - WOC - RIH OE to 639 mMD, TOC tagged. - Circulation - POOH OE to surface - RIH 8-1/2" TCB + BHA Rotary to 639 mMD - DOC to 679 mMD | - DOC to 718 mMD | - DOC to 768 mMD - Circulation - POOH 8-1/2" TCB + BHA Rotary to surface - M/U 6" TCB BHA + Rotary to 768 mMD, DOC to 1397 mMD.
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | Haryo Abiyoso |  |  |  | - R/U (H-3) : 31% | - R/U 100%
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | M. Reyhan W. / Donny Y. |  |  | - R/D (H-3): 58% |  | - R/D 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-20), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on FID est March 2026
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-63). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Ari Welas/Darwis YB/M.Feisal | 21 | 1008 mMD/991.7 mTVD | - DOC to 525 mMD, no drilling progress. - Circulation - POOH 17-1/2” TCB + BHA Rotary to surface - M/U & RIH 17-1/2" Milling Assy to 525 mMD - Perform milling 17-1/2" to 530 mMD | - Perform milling 17-1/2" to 533 mMD | - Dress out interval 525-537 mMD - POOH 17-1/2" Milling assy to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-63), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III