## Sheet1
Field | Well Name | Location Name | Rig Name | Company Man | Days | Depth | Summary | Current Status | Next Plan
JATIBARANG | AMJ-004 | AMJ-4T | WBR-01 | Ade Rama / Heru Sulistyo / Herry Prabowo | 30 | 1462 mMD/ 1367 mTVD | - DOC to 769 mMD - Circulation - POOH 8-1/2" TCB + BHA Rotary to surface - RIH 6" TCB BHA + Rotary to 769 mMD - DOC to 780 mMD - Circulation - P/T casing 700 psi, hold. - DOC to 788 | - DOC to 810 mMD - P/T casing, in progress. | - DOC to 1397 mMD. P/T at 1370 mMD - RIH to RS 1397 mMD - Circulation - POOH 6" TCB BHA + Rotary to surface
JATIBARANG | PCT-Y | PCT-Y | PDSI #04.3/N110-M | Haryo Abiyoso |  |  |  | - R/U (H-4) : 34% | - R/U 100%
JATIBARANG | BDA-008 | BDA-D1 | PDSI #12.3/N110-M | Donny Y. |  |  | - R/D (H-4): 83% |  | - R/D 100%
JATIBARANG | AMJ-B1 |  | PDSI #31.3/D1500-E | - |  |  | - Rig Idle (H-21), Rig idle at location ABG-H4 while Inpection Rig Category III - Wait on construction readiness for location AMJ-B1 (progress : 15%), est. Ready on M4 February 2026 - Wait on FID est March 2026
JATIBARANG | KRE-002ST |  | PDSI #09.2/N80UE | - |  |  |  | - Rig Idle (H-64). Rig Idle at Location CMR-STOB. - Wait on construction readiness for location KRE-02ST. Est M2 Feb 2026 (Progress: 18%) - Wait on FID est May 2026 | - Rig Idle.
SUBANG | BMH-002 | BMH-INF1 | PDSI #15.3/N110-M | Ari Welas/Darwis YB/M.Feisal | 22 | 1008 mMD/991.7 mTVD | - Perform milling 17-1/2" to 537 mMD - Circulation - POOH 17-1/2" Milling assy to surface - RIH 17-1/2" TCB + 18-1/2" Watermelon to 511 mMD. Redress interval 484-511 mMD | - RIH 17-1/2" TCB + 18-1/2" Watermelon to 526 mMD. Redress interval 511-526 | - RIH 17-1/2" TCB + 18-1/2" Watermelon to 537mMD - Dress out 526-537 mMD - Circulation - Drop gyro - POOH 17-1/2" TCB + 18-1/2" Watermelon to surface
SUBANG | TGP-INF1 | TGP-INF1 | PDSI #28.2/D1000-E | - |  |  |  | - Rig Idle (H-64), Rig Idle at Location BJR-D3. - Wait on construction readiness for location TGP-INF1, Tegal Pacing. Est. M4 Maret 2026 (Progress: 9%) | - Rig Idle, inspection CAT III