## Sheet1
No | Nama Sumur | Nama Rig | Hari ke | Kedalaman (mMD) | Progress (mMD) | AFE | Realiasi Biaya | EMD | Summary Report | Cuurent Status | Next Plan
1 | MDP-1x | ASIAN ENDEAVOUR-1 | 105 | 4738 | 4260 | 45414090 | 40456592 | 2026-01-25 | PRESSURE BUILD UP PERIOD. | PRESSURE BUILD UP PERIOD. | SLICKLINE MPLT SHUT IN & MULTIFLOW. COMMERCIAL FLOW. WELL KILLING.
2 | SS-505-aSH1.T1 | TASHA | 60 | 4279 | 4258 | 23847541 | 19712836 | 2026-01-15 | R/D 7" POWER TONG & HANDLING EQUIPMENT - RIH 7" x 3½" LINER ASSY IN CASED HOLE TO 3576 mMD - CIRC - RIH 7" x 3½" LINER IN OPEN HOLE TO 4242 mMD - M/U CMT HEAD ASSY - SPACE OUT TO LINER SETTING DEPTH. | CIRC CONDITIONING MUD. | SET 7 IN LINER HANGER, PERFORM 3.5 IN LINER CEMENT JOB
3 | NB-701-bSH2 | Zhong You Hai – 16 | 14 | 2679 | 2681 | 17892620 | 5544232 | 2026-02-08 | DRILL 8½" X 9½" HOLE FROM 2254 mMD TO TD AT 2681 mMD/ 2533.7 mTVD - CIRC HOLE CLEAN - PERFORM LCT (OVB) - DEACTIVATE XR800 REAMER - PUMP OOH 8½" X 9½" RSS BHA TO 2081 mMD. | PUMP OOH 8½" X 9½" RSS BHA AT 1300 mMD. | TRIP OUT & L/D BHA - PERFORM PT/FA LOGGING - RIH 7" LINER.
4 | TN-S62 | RAISIS 102 | 6 | 4198 | 1164 | 6059059 | 2057152 | 2026-01-19 | DRILL 12¼" HOLE TO SECTION TD AT 1164 mMD/ 1035.2 mTVD - CIRC HOLE CLEAN - F/CHECK - SPOT HIVIS - BACKREAM OOH 12¼" MOTOR BHA TO 329 mMD. | CONT L/D 12¼" MOTOR BHA | RIH 9-5/8" CSG - LAND CSG HGR - R/D CRT - SET PACK OFF - N/D DIVERTER
5 | TN-AA763 | YANI RIG 104 | 8 | 2554 | 2544 | 4886185 | 2885884 | 2026-01-03 | RIH 3-1/2" TUBING F/ 213 mMD TO 2548 mMD. M/U TEMP JOINT. CIRC HOLE. M/U RIH & LAND TUBING HANGER. LOCK & OVERPULL TEST 3-1/2" TBG HGR. CIRC TEST. L/D LANDING JOINT & R/D 3-1/2" TBG HANDLING EQUIPMENT. N/D DIVERTER. L/D TUBULAR ON DERRICK. | CONT' L/D ALL TUBULARS ON MAST. | L/D ALL TUBULARS ON MAST. BALLASTING RIG.