## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name [2] | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Summary Report | Current Status | Next Plan | Report Date | Operation Date
INC | Region 1 | Zone 1 | PEP | APS-752 | RNT-DZ51 | P-475 | Development | Onshore | [5 empty] | Persiapan inspeksi kategori 3 |  | Rig Down 100%. Inspeksi Kategori 3. Note: - Operasi secure well di lokasi RNT-DZ51/P-475 telah selesai, Rig APS #752 dinyatakan release sementara TMT 08 Februari 2026 Pkl: 24.00 WIB. - Perbaikan lokasi sudah selesai 21 januari 2026, alat berat vibro dan excavator di demobilisasi 21 januari 2026. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ACS-009 | Rig ACS-009 Activity at Yard | Rig ACS-009 Activity at Yard | Development | Onshore | [5 empty] | Yearly maintenance YM progress : 74.38% (based on latest QAQC report on 11 Feb 2026) Update Action Items Post Incident IDB-07 : > Progress to complete action items from Memorandum 092/PHE20000/2025-S0 (Action item point 1-9) : 83.1.% > Progress to complete action items from DWI PHR Zona Rokan (Action item point 10-12) : 100% > Progress to complete ALL action items (Action item point 1-12) : 87.3% |  | Continue Yearly maintenance | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ACS-019 | Duri 11519 | 5H-0305B | Development | Onshore | [5 empty] | Drilling 11-3/4", Circulate Hole Clean, POOH & R/B string,Logging Job. |  | Gravel Pack Jobs, Prepared for tubing pump running, RIH tubing pump, land and test tubing hanger for 650 psi, release and L/D Tubing, N/D Class III BOP, RIH Plunger and Sucker Rod | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ACS-023 | Rig ACS-023 Yearly Maintenance | Rig ACS-023 Yearly Maintenance | Development | Onshore | [5 empty] | Progress to complete ALL action items (Action item poin 1-12) 89.8% |  | Continue yearly maintenance | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ACS-024 | Balam So 00694 | P_BLSO25_0047LQR | Development | Onshore | [5 empty] | 100% R/U rig & equipments. Spud in Well BLSO-0694. Stand up tubular. M/U 12-1/4" Clean out BHA #1. Clean out. CHC. TOH BHA#1. M/U 12-1/4" Directional BHA#2 | M/U 12-1/4" Directional BHA #2 | DOF 12-1/4” HS to CP. CHC. TOH & L/D Directional BHA#2. R/U Csg running tools. RIH 9-5/8" Csg. R/U Cementing Head. Cementing Job. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ACS-026 | Rig ACS-26 Activity at Yard | Rig ACS-26 Activity at Yard | Development | Onshore | [5 empty] | Yearly Maintanence 82.25%, Rig Standby for step back to strengthen operational safety. Cummulative progress to complete all action item 87.5% |  | Cont' Yearly maintenanceRig Standby for step back to strengthen operational safety. Cummulative progress to complete all action item | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ARJ-01 | Rig ARJ-01 Mobilization / Activity at Yard | Rig ARJ-01 Mobilization / Activity at Yard | Development | Onshore | [5 empty] | Cont'd Yearly Maintenance at ARJ yard and loc 5E-0808A (44.8%) * YM Plan (Rev9)/ Actual: 88 days/ 70.25 days Summary progress for closing action items post incident IDB-07: 1) Progress to complete action items from memorandum 092/PHE20000/2025-SO (Action item poin 1-9) = 62% 2) Progress to complete action items from DWI PHR Zona Rokan (Action item poin 10-12) = 93% 3) Progress to complete ALL action items (Action item poin 1-12) = 70% |  | at 05:00 hrs: Yearly maintenance | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | ARJ-02 | Rig ARJ-02 Mobilization/Activity at Yard | Rig ARJ-02 Mobilization/Activity at Yard | Development | Onshore | [5 empty] | Yearly Maintenance |  | Continue Yearly maintenance | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-18 | Minas 02191 | P_MINA25_0004HW | Development | Onshore | [5 empty] | Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1. | Cumulative Progress All Action Items 69.9% | Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-19 | Libo Se 00088 | P_LISE25_0041 | Development | Onshore | [5 empty] | Contd RIH 9 5/8" csg (stop at 580'MD), TOH & L/D 9-5/8" csg, C/O upper IBOP of TDS, Wait on PHR 12-1/4 TCB from Baung (broken). Prepared another PHR 12-1/4" TCB, took from BDSI-27 Minas. | TIH 12-1/4 TCB (open nozzle) w/slick BHA | Contd TIH 12-1/4" TCB (open nozzle) w/slick BHA, CHC at bottom. POOH, 2-1/4" TCB (open nozzle) w/slick BHA to surface | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-21 | Kotabatak 00573 | P_KOTA25_0002HW_MSF | Development | Onshore | [5 empty] | 98% R/U Rig and equipment. |  | Continue R/U Rig and equipment | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-27 | Minas 02190 | MINAHW24_P09 | Development | Onshore | [5 empty] | Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1. Cumulative progress to complete All action items: 86 %. | Shutdown rig due to unsafe condition/manner | - Continue Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1. - R/D 100% on MINA 2187. MOMI to MINA 2190 (4A-45A). | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-28 | Kotabatak 00574 | P_KOTA26_0002INJ | Development | Onshore | [5 empty] | Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1 Noted -Zero rate applies to the rig for this period -Activities for step-back strengthening operational safety aspect Cumulative progress to complete ALL action items 91 % | Shutdown rig due to unsafe condition/manner | Continue Follow up Quick wins and Action item post insiden IDB-07.Resume Rig operation mode.R/D Rig equipment at Rangau-32.Moving to Kota Batak 0574 | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-60 | Petani 00264 | P_PETA25_0009HW | Development | Onshore | [5 empty] | 45% MOMI Rig & Equipment to Petani-264 | 53% MOMI Rig & Equipment | 100% MOMI to Petani-264. 100% R/U Rig & Equipment. Spud In Well Petani-264. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BDSI-61 | Petani 00265 | P_PETA25_0007HW | Development | Onshore | [5 empty] | TIH 18-5/8" Casing. M/U 18-5/8" Casing Swadge. Circulate. N/D 18-5/8" Casing Swadge. C/O TDS link & R/U 5" DP Handling Tool. TIH Stinger. R/U Cementing Head. Cementing Job. Flush Conductor, R/D cementing line. TOH Stinger & Flush DP string. Cut 24" Conductor Pipe (In Progress) | Install Starter Head | N/U 21-1/4" BOPE, Full Test BOPE (w/ Test Casing), Stand Up Additional Tubular, M/U & TIH 17-1/2" Directional BHA#3, DOC | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BN-05 | Rig BN-05 Yearly Maintenance | Rig BN-05 Yearly Maintenance | Development | Onshore | [5 empty] | Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1. |  | Shutdown rig due to unsafe condition/manner performed by rig contractor as per Body of Contract Clause No. 6.7.1. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | BN-18 | Minas 02189 | P_8D-19E | Development | Onshore | [5 empty] | 79% MOMI (49 of 62 loads) to Minas 8D-19E. | 82% MOMI | 100% MOMI from Minas 10D-46 to Minas 8D-19E | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | GW-336 | Bangko 00545 | P_BNKO_LQR_P5F | Development | Onshore | [5 empty] | 15% R/U Rig & Equipment at BNKO00545 P_BNKO26_LQR_P5F). After midnight: 20% R/U Rig & Equipment at BNKO00545 P_BNKO26_LQR_P5F). | 20% R/U Rig & Equipment | Continue 100% R/U Rig & Equipment at BNKO00545 (P_BNKO26_LQR_P5F). | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | GW-337 | Balam So 00696 | P_BLSO25_0032LQR | Development | Onshore | [5 empty] | Continue 15% R/D Rig & Equipment at BLSO-0697 |  | Continue 100% R/D Rig & Equipment at BLSO-0697 & Skid Move to BLSO-696 | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | GW-338 | Bangko 00550 | P_BNKO26_LQR_PX104A | Development | Onshore | [5 empty] | Cont'd L/D BHA Anadrill, Prepare casing tool, RIH 9-5/8" casing, Cementing 9-5/8", R/D CMT Head, Cut & L/D Exc Casing, N/D Bell Nipple, Install Casing Clamp, Install Casing Head, WO Crew Completeness. | N/U BOP | N/U BOP,Pressure Test BOP,M/U & TIH 8-1/2" PDC Bit on Steerable BHA#3 to TOC, Choke drill,DOC + 5 ft New formation,FIT, DOF 8-1/2" HS | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | GW-339 | Bangko 00546 | P_BNKO26_LQR_PX104D | Development | Onshore | [5 empty] | 46% MOMI f/ MENO-00077 to BNK-546 (34 Loads of 73 Loads), 5% R/U progress rig and equipment. |  | Continue 100% MOMI from MENO-077 to BNKO-546. R/U Rig equipment | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | PDSI-49.2 | Bangko 00548 | P_BNKO26_LQR_PX58A | Development | Onshore | [5 empty] | 90% R/U and equipment at BNKO 548 | 90% R/U and equipment at BNKO 548 | Cont'd to 100% R/U and equipment at BNKO 548, Spud in well BNKO 548, Stand up 5" HWDP, M/U 12.25" Clean out BHA, Clean out Conductor, M/U 12.25" Directional BHA and tested, DOF to CP, CHC, TOH and L/D 12.25" Directional BHA. Run 9-5/8" Casing, Cementing job 9-5/8" Casing. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | PDSI-50.2 | Bekasap 00250 | P_BEKA26_0006 | Development | Onshore | [5 empty] | 45% MO/MI rig and equipment from BEKA 245 to BEKA 250 |  | Continue MO/MI from BEKA 245 to BEKA 250, R/U rig & equipment at BEKA 250 | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | PDSI-51.2 | Balam So 00692 | P_BLSO25_0056LQR | Development | Onshore | [5 empty] | 70% R/U Rig and Equipment at BLSO-692. After midnight: Continue R/U Rig and Equipment at BLSO-692 |  | 100% Rig up Rig and equipment, Spud in | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | PDSI-52.2 | Rig PDSI 52.2 Activitiy at Yard | Rig PDSI 52.2 Activitiy at Yard | Development | Onshore | [5 empty] | Equipment maintenance. Rig Carrier and Mast progress 96.37%. Cumulative progress to complete all action items regarding operational safety strengthening: 68% | WO daylight to cont acitivity at PDC Yard | Equipment Maintenance | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | PDSI-53.2 | Prima 00005 | P_ASTR25_02 | Development | Onshore | [5 empty] | Cont TOH 9-5/8" Casing from 747 ftMD to surface (Cased Hole). R/D casing handling tools. M/U and TIH 12-1/4" Trip BHA #4 to 3669 ftMD. After Midnight: Cont'd TIH 12-1/4" Trip BHA #4 |  | Cont'd TIH 12-1/4" Trip BHA #4 to bottom. CHC, Flow Check. TOH & L/D 12-1/4" Trip BHA #4. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 2&3 | PHR | PDSI-54.2 | Pudu 00024 | P_PUDU26_05 | Development | Onshore | [5 empty] | Shutdown rig for step-back strengthening operational safety aspects. Cummulative progress to complete ALL action items 77.62% |  | Continue shutdown rig for step-back strengthening operational safety aspects | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | ACS-21 | KRG-038 | KRG-PE2 | Development | Onshore | [5 empty] | Lanjut bor lubang berarah dengan 12-1/4" PDC Bit + BHA DD dari 994 mMD sampai 1108 mMD/1077 mTVD (CP). Sirkulasi. Perbaikan MP#2. Sirkulasi. Cabut 12-1/4" PDC Bit + BHA DD dari 1108 mMD sampai 1050 mMD. | Lanjut cabut 12-1/4" PDC Bit + BHA DD dari 1050 mMD sampai 822 mMD. | Lanjut cabut rangkaian 12-1/4" PDC Bit + BHA DD sampai permukaan. R/U CDS. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | AMS-01 | BN-B26 | BN-B26 | Development | Onshore | [5 empty] | H-23: Rig Maintenance, Kum: 61%. ROL (Rig on Location): Sumur KRG-037 (Lokasi KRG-PJ1). |  | Lanjut Rig Maintenance dan persiapan moving ke BN-B26. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | ARJ-28 | ALR-001 | ALR-001 | Exploration | Onshore | [5 empty] | Perbaikan dan uji fungsi Mud Pump#1, #2 dan #3. |  | Lanjut persiapan lokasi buat set up Mud Pump#1, #2, #3 (Pengganti). Uji fungsi Mud Pump#1, #2 dan #3 (Pengganti). Cabut rangkaian 8-1/2" PDC RR bit + Rotary BHA. M/U dan Masuk rangkaian 8-1/2" PDC + BHA DD sampai 1158 mMD. Lanjut bor lubang 8-1/2" sampai 1387 mMD. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | Airlangga-55 | MJ-INJ1 | MJ-INJ1 | Development | Onshore | [5 empty] | H-4: Rig Move, Kum 85.66%. - Rig Down: Kum 100%. - Rig Move: Kum 100%. - Rig Up: Kum 57%. |  | Lanjut Rig Move ke Lokasi MJ-INJ1 100% (include R/D, R/M, R/U). | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #01.2/N80B-M | TMB-PG3 | TMB-PG3 | Development | Onshore | [5 empty] | H-4: Rig Up, Kum: 90%. |  | Lanjut Rig Up 100% di lokasi TMB-PG3. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #05.2/OW760-M | ABB-145 | ABB-A8 | Development | Onshore | [5 empty] | P/T BOP Group 13-5/8" x 5K. Masuk rangkaian 8-1/2" PDC Bit + BHA DD (RSS + LWD) sampai 1399 mMD. Bor plug, FC, dan cement shoetrack dari 1399 mMD sampai 1401 mMD/1282.95 mTVD. | Lanjut bor cement shoetrack dan RS dari 1401 mMD sampai 1424 mMD/1303.24 mTVD. | Lanjut cement shoetrack, RS & 3 meter formasi baru sampai kedalaman 1431 mMD. Sirkulasi SG in/out 1.26 SG. Leak Off Test. Lanjut bor formasi lubang berarah 8-1/2" sampai kedalaman +/- 1930 mMD (TD). | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #16.2/NT45-M | MJ-A11 | MJ-166 | Development | Onshore | [5 empty] | Lanjut masuk 6" TCB + BHA Rotary dari 364 mMD sampai 1010 mMD. Sirkulasi. Cabut 6" TCB + BHA Rotary dari 1010 mMD spi ke permukaan. Masuk 6" TCB + BHA Scraper 7" sampai 1010 mMD. Sirkulasi dan ganti isi lubang dengan CF 1.26 SG. Cabut 6" TCB RR + BHA Scrapper 7" dari 1010 mMD sampai 366 mMD. | Lanjut cabut 6" TCB + BHA Scrapper 7" dari 366 mMD sampai permukaan. Pekerjaan CH Logging 7" GR-CCL-VBL-CDL-USIT. | Lanjut CH logging casing 7" (CBL-USIT). Evaluasi bonding cement. Perforasi produksi lapisan PLB-I3 (755 – 756 mMD), PLB-H1 (622 – 623.5 mMD), dan PLB-G2.1 (561 – 562 mMD & 564.5 – 566.5 mMD). | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #17.2/NT45-M | MJ-A7 | MJ-A7 | Development | Onshore | [5 empty] | H-2: Pre-Rig Up, Kum: 15%. Sambil Rig Maintenance, progress: 93.3%, dan closing temuan team QC, progress kum: 93.7%. |  | Lanjut Pre-Rig Up di lokasi MJ-A7 sambil Rig Maintenance dan closing finding team QC. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #18.2/LTO650-M | MSI-MP14 | MSI-MP14 | Development | Onshore | [5 empty] | H-44: Rig Maintenance (progress: 90.5%) dan Inspeksi Kategori-3 (progress: 100%, closing kum: 74.57%) sambil persiapan moving ke Lokasi MSI-MP14. ROL (Rig on Location): BN-140 (BN-B16). |  | Lanjut Rig Maintenance dan Inspeksi Kategori-3 sambil persiapan moving ke Lokasi MSI-MP14. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #20.2/EMSCOD2-M | KMBR-001 | KMBR-001 | Exploration | Onshore | [5 empty] | Lanjut RIH DST #2 + TCP BHA dari 856 sampai 1141 mMD. Pressure test #4 string DST #2 @ 1141 mMD dengan 5000 psi selama 15 menit dengan cementing unit, baik. Lock Open SFTTV. Sirkulasi lurus melalui string dengan 160 gpm / 450 psi, konfirm SFTTV lock open. PJSM, R/U ELNUSA wireline unit. Korelasi-1 RA Marker BHA = 1076.93 mMD. RA Marker Wireline = 1083.03 mMD. Rangkaian DST #1 terlalu dalam 6.1 mMD. Space out. M/U 2 ea PJ PH-6 tubing 2.07 m + 2.38 m. N/U Flow head. Displace string with N2. Set 7" Packer at 1073 mMD. P/T annulus 1200 psi, 15 menit, baik. Buka FOSV dan master valve. Line up surface testing line to flow head. Bleed off N2 from 1570 to 0 psi. Korelasi-2 RA Marker BHA = 1076.93 mMD. RA Marker Wireline = 1076.54 mMD. Rangkaian DST #1 lebih dangkal 0.39 mMD. POOH & L/D CCL-GR. R/D Wireline sheaves. Persiapan Drop bar. R/U scaffolding. Naikan Pcsg 250 psi. PJSM, Drop bar untuk perforasi interval 1119-11124 mMD & 1130.5-1135 mMD dengan 4-1/2" TCP, HMX 5 SPF, getaran terasa di RF. Observasi tertutup Pwh/Pcsg/WHT : 3 psi/140 psi/78 degF | PJSM, R/U PCE + Lubricator Slickline. Pwh/Pcsg/WHT: 16 psig/ 131 psig/ 77 DegF. Masuk 1,4" JDC pulling tool duduk di kedalaman 1111 mMD, 80 klbs. Angkat rangkaian 1,4" JDC pulling tool di dapatkan tension bertambah dari 300 klbs menjadi 340 klbs, indikasi stem bar berhasil didapatkan. Pwh/Pcsg/WHT: 35 psig/ 111 psig/ 76 DegF. Cabut 1,4" JDC pulling tool sampai permukaan, Stem bar didapatkan di permukaan. L/D drop bar stem. Pwh/Pcsg/WHT: 43 psig/ 107 psig/ 76 DegF | Observasi tertutup. Observasi terbuka / Initial flow. RIH EMR sambil SGS | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #25.2/LTO750-M | TMB-026 | TMB-PG4 | Development | Onshore | [5 empty] | Lanjut masuk 6" TCB + BHA Rotary dari 728 mMD sampai 1637 mMD (LC). Sirkulasi. Cabut 6" TCB + BHA Rotary dari 1637 mMD sampai permukaan. Masuk 6" TCB + BHA Scrapper tandem 7" & 9-5/8" sampai 981 mMD. | Lanjut masuk 6" TCB + BHA Scrapper tandem 7" & 9-5/8" 981 sampai 1402 mMD. | Lanjut masuk rangkaian 6" TCB + scraper tandem 7" & 9-5/8" sampai kedalaman 1637 mMD (LC). Sirkulasi, displace ganti isi lubang dengan CF 1.01 SG. Cabut rangkaian 6" TCB + BHA Scrapper tandem 7" & 9-5/8" sampai permukaan. Pekerjaan CH logging 7" CSG (GR-CCL-CBL-VDL-USIT) & 9-5/8" CSG (GR-CCL-CBL-VDL). Pekerjaan CH logging VSP. N/D BOP groups 13-5/8" x 5K. N/U THS 11" x 7-1/16" - 3K. N/U BOP 7-1/16" x 5K. F/T & P/T BOP group 7-1/16" x 5K. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #29.3/D1500-E | BTG-030 | BTB-Q | Development | Onshore | [5 empty] | Lanjut masuk rangkaian pipa produksi 2-7/8" Tubing + 7" Packer SG dari 750 mMD sampai 1701.89 mMD. Set 7" Mech-Packer SG, P/T Packer, Ok. N/D BOP Group 7-1/16" x 5K Psi. N/U X-Mastree 3-1/8"-5K x 2-1/16"-5K Psi. L/D Tubular. Persiapan & Set Up unit CTU dan BBS. | Lanjut persiapan & Set Up unit CTU dan BBS. | Lanjut persiapan Set Up unit CTU dan BBS. Install Streamline & line produksi. Rig up CTU, Unload CF menggunakan N2. Uji Produksi. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #30.2/D1000-E | PMN-I | PMN-I | Development | Onshore | [5 empty] | H-19: Inspeksi Kategori-3 (progress kum: 100%. Closing Inspeksi Kategori-3, kum: 100%) dan Lifting Gear Inspection (progress kum: 75%) sambil menunggu kesiapan lokasi PMN-I (progress: 76.86 %, estimasi selesai di M3 Februari 2026). ROL (Rig on Location): TLJ-260 (Lokasi TLJT-05). |  | Lanjut LGI colour coding sambil menunggu kesiapan Lokasi Sumur PMN-I. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #32.2 / N80UE-E | LM-03 | LM-03 | Development | Onshore | [5 empty] | H-3: Rig Maintenance (progress: 26.33%) sambil menunggu kesiapan lokasi LM-03 (progress: 91.95%, est selesai M1 Maret 2026). ROL (Rig on Location): ABB-144 (ABB-T2). |  | Lanjut Rig Maintenance sambil menunggu kesiapan lokasi LM-03. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #39.3/D1500-E | BNG-078 | BNG-A19 | Development | Onshore | [5 empty] | Lanjut masuk 8-1/2" PDC Bit + BHA DD (RSS+MWD+LWD) dari 42 mMD sampai 1732.50 mMD. Bor Plug, FC, Shoe Track dan RS dari 1732.50 mMD sampai 1763 mMD/1655.86 mTVD. Sirkulasi. LOT, EMW 2.09 SG. Lanjut bor formasi berarah lubang dengan 8-1/2" PDC Bit + BHA DD dari 1763 mMD sampai 1769 mMD/1661.42 mTVD. | Lanjut bor formasi berarah lubang dengan 8-1/2" PDC Bit + BHA DD dari 1769 mMD sampai 1809 mMD/1698.48 mTVD. | Lanjut bor berarah lubang 8-1/2" sampai 2713.65 mMD (est TD). | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #41.3/N110UE | BNG-A10 | BNG-A10 | Development | Onshore | [5 empty] | H-4: Rig Move dari lokasi BNG-37T ke lokasi BNG-A10. - M/O: Kum 27 Load (19.2%). - M/I: Kum 10 Load (7.2%). - Est total: ± 140 Load. Sambil rig maintenance (progress: 95.7%), Inspeksi kategori-3 (progress: 100%), dan Inspeksi colour coding (LGI) oleh Satoil (progress: 80%). |  | Lanjut Rig Move dari lokasi BNG-37T ke lokasi BNG-A10, sambil rig maintenance dan LGI. | 2026-02-12 | 2026-02-11
INC | Region 1 | Zone 4 | PEP | PDSI #42.3/N1500-E | BNG-D14 | BNG-D14 | Development | Onshore | [5 empty] | H-31: Pre-Move Rig dari lokasi GNK-PD29 ke lokasi BNG-D14 sambil menunggu kesiapan lokasi BNG-D14 (progress konstruksi 21.46%, estimasi selesai di M2 Maret 2026), Inspeksi (LGI) colour coding (progress: 100%), dan Rig Maintenance (progress: 99%). - ⁠M/O: Kum 99 Load (78.5%). - ⁠M/I: Kum 84 Load (67%). - ⁠Est total: ± 126 Load. |  | Lanjut Pre-Move Rig sambil menunggu kesiapan lokasi BNG-D14, Inspeksi (LGI) colour coding, dan Rig Maintenance. | 2026-02-12 | 2026-02-11