## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | R/U TRS tools. RIH 13.3/8" casing from surface to 439 m. Performed cementing job. R/D cementing equipment. Performed cut on 13.3/8" casing. |  | N/U BOP. P/T BOP-WH flange. M/U 12.1/4" BHA #3 & RIH to TOC. Displace 1.07 sg WBM by 1.23 sg OBM. Drill out cement. Drill 12.1/4" hole section as per program. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | Directional drilling 12 1/4" section from 731m to 1373m , Circ & spot LCM pill, performed FIT at 12 ppg EMW, drilled a head to 2037m. |  | Directional drilling 12 1/4" hole to section TD~2595 m, Circ hole clean, POOH. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-613 | WQ-613 | Development | Onshore | 2025-12-03 |  |  |  |  | Drilled 6­1/8” horizontal section through Mishrif formation from 3838 m to 4488 m, No downhole losses. |  | Drill 6­1/8” horizontal section through Mishrif formation as per directional plan to well TD at 4865 M. Circulate hole clean. Perform wiper trip to 2884 m, RIH back to bottom. Circulate hole clean and displace open hole with 1.05 sg brine. POOH to 7" liner shoe at 2884 m, displace well by inhibited water of 1.0 SG, POOH 6-1/8" directional BHA to surface and L/D same. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | Drilled out 7" shoe track from 2726 m to 2795 m (10 above the liner shoe). Circulated hole clean. Set 7" Liner Top Packer. Scraped the casing up to 2540 m. Reamed down to the bottom. Circulated hole clean. POOH 6" clean out BHA w/ 7" casing scrapers to 320 m. |  | Perform cement evaluation WL logging operations. P/U, M/U and RIH 6-1/8'' DIR BHA on 4'' DP Stands + 5.5'' DP Stands to 2795 m. P/T casing to 2500 psi. Drill shoe track and rat hole Drill 6-1/8" Lateral Hole Section as per directional Plan. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | POOH 8-1/2" Core BHA#13 from 2637 m to surface and lay down the same, retrieved core recovery 100% with 53 m and Accumulative core recovery 300.42 m, RIH 5-1/2" DP kill string, Perform slip and cut drilling line on going. |  | Perform slip and cut drilling line, P/U and M/U 8-1/2" Directional Logging BHA and RIH to bottom, Perform logging for open hole section to 2637 m ( Well TD) . Circulate hole clean. POOH 8-1/2" logging BHA to surface. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Circulated hole clean, POOH 17-1/2" Dir BHA to surface and L/D same. L/D riser and flow line, R/U NE tools, P/U & M/U & RIH 13-3/8" Casing to 897 m. Landed CHH with landing joint at 911 m. Circulated the hole clean. R/U cement head and lines. Performed 13-3/8'' cement job. |  | Perform cement job as per program. L/D NE tools, Connected 2-1/16'' SOV on CHH. N/U 13-5/8"10 K BOP stack. P/T BOP connections. Install wear bushing. P/U, M/U & RIH 12-1/4'' directional BHA. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | [5 empty] | Rig Down and Mobilization operations from WQ1-599 to WQ1-600. R/D %: 100, R/M %: 95, R/U: 43%. Expected Spud date 10th January-2026. |  | Continue Rig Down and Mobilization operations from WQ1-599 to WQ1-600. | 2026-01-04 | 2026-01-03
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | Continued drilling 8-1/2" hole to 1418m. |  | Continue drill 8-1/2" hole to section TD at ±1756m. | 2026-01-04 | 2026-01-03