## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | Cut 13.3/8" casing. N/U and P/T WH. N/U and P/T BOP. Installed wear bushing. M/U and RIH BHA #3 with 12.1/4" drill bit from surface to 167 m. |  | Drill out shoetrack & rat hole. Drill 12.1/4" hole section as per program. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | Directional drilling 12 1/4" hole section from 1878m to 2524m. |  | Directional drilling 12 1/4" hole to section TD~2595 m, Circ hole clean, POOH. to surface with L/D 12 1/4" BHA, Perform WL logging Run #1. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-613 | WQ-613 | Development | Onshore | 2025-12-03 |  |  |  |  | Drilled 6-1/8" horizontal section through Mishrif formation from 4488 m to 4863 m (well TD), Circulated hole clean. Performed wiper trip: POOH 6-1/8" Directional BHA to 4340 m. No downhole losses. |  | Perform wiper trip to 2884 m, RIH back to bottom. Circulate hole clean and displace open hole with 1.05 sg brine. POOH to 7" liner shoe at 2884 m, displace well by inhibited water of 1.0 SG, POOH 6-1/8" directional BHA to surface and L/D same. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | POOH 6" Clean-out BHA to surface. L/D same. R/U wireline tools and pressure tested the same. RIH to 2690 m, obstruction was observed. POOH wireline tools to surface. |  | Perform full BOP pressure test. P/U, M/U and RIH 6-1/8'' Directional BHA on 4'' DP stands + 5.5'' DP stands to 2795 m. P/T casing to 2500 psi. Drill shoe track and rat hole Drill 6-1/8" lateral hole section as per directional plan. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | Performed slip and cut drilling line, P/U and M/U 8-1/2" Directional Logging BHA and RIH to 2172 m, Performed logging of 8-1/2" open hole section to 2451 m. |  | Performing logging for 8-1/2" open hole section to 2637 m (Well TD). Circulate hole clean. Perform wiper trip to casing shoe and RIH to bottom, Circulate hole clean, POOH 8-1/2" logging BHA to surface. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Performed cement job as per program. L/D NE tools, Connected 2-1/16'' SOV on CHH. N/U 13-5/8" 10K BOP stack. P/T BOP connections, OK. Installed wear bushing. P/U, M/U & RIH 12-1/4'' directional BHA to 500 m. Performed shallow test for MWD tools. Conducted Mustering combined drill (H2S and Choke) with both shifts. RIH 12-1/4'' directional BHA and tagged TOC at 865 m. Drilled out cement, shoe track and rat hole to 913 m. |  | Drill 12-1/4'' hole section as per directional plan. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | [5 empty] | Rig Down and Mobilization operations from WQ1-599 to WQ1-600. R/D %: 100, R/M %: 100, R/U: 62%. Expected Spud date 10th January-2026. |  | Continue Rig Down and Mobilization operations from WQ1-599 to WQ1-600. | 2026-01-05 | 2026-01-04
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | Continued drilling 8-1/2" hole to section TD at 1751m. Circulated hole clean. Performed DLOT. Increase MW from 8.6 ppg to 9.2 ppg. |  | Spot EZSqueeze while SOOH to 9-5/8" casing shoe. Replace RCD BA. Perform hesitation squeeze. RBIH. Circulate hole clean. Rollover mud to 9.5 ppg. Spot LCM while POOH to 9-5/8" casing shoe. Circulate well clean. Retrieve RCD BA. POOH. | 2026-01-05 | 2026-01-04