## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | RIH BHA #3 from 167 m to 425,5 m and tagged TOC. Drilled out cement to 440 m. Drilled 12.1/4" new hole section from 440 m to 930 m. |  | Drill 12.1/4" hole section as per program. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | Directional drilling 12 1/4" hole to section TD at 2581m, Circ hole clean, spotted Hi-vis, POOH BHA #3 with backreaming to 1002m. |  | Continue POOH to 13 3/8" csg shoe 399m recording SONIC, RIH back for wiper trip, CHC & POOH to surface, L/D BHA, Perform WL logging Run #1. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-613 | WQ-613 | Development | Onshore | 2025-12-03 |  |  |  |  | Performed wiper trip POOH 6-1/8" directional BHA from 4340 to 2884 m, RIH back to bottom at 4863 m. Circulated hole clean for one cycle. displaced the open hole with 1.05 SG brine. POOH 6-1/8" directional BHA to 2655 m, performed wiper trip RH from 2655 m to 2884 m, displaced cased hole with 1 SG inhibited water. |  | Displace cased hole with 1 SG inhibited water, POOH 6-1/8" Directional BHA to surface and L/D same. R/U WL tools, Perform 7" casing cement evaluation log operations, POOH WL tools string to surface. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | Rigged down WL logging tools. P/U, M/U and rack back 29 stands of 4" DP. Retrieved wear bushing. Performed 13-3/8'' BOP test. Installed wear bushing. P/U, M/U and RIH 6-1/8" Directional BHA with 4" DP single by single to 1100 m. |  | Drill shoe track + rat hole. Drill 6-1/8" Lateral hole section as per directional plan. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | Performed logging for 8-1/2" open hole section to 2637 m (Well TD). Circulated hole clean. Performed wiper trip to 2172 m and RIH to bottom, circulate hole clean on going. |  | Circulate hole clean, POOH 8-1/2" logging BHA to surface and L/D the same, Perform WL logging for open hole as per program. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Drilled 12-1/4'' hole section as per directional plan from 913 m to 1365 m. Circulated hole clean, downhole losses 6-8 m3/hr. POOH 12-1/4'' Dir BHA on elevator from 1365 m to 1135 m. Activated PBL and spotted 20 m3 of 180 ppb LCM. POOH 12-1/4'' Dir BHA on elevator from 1135 m to 786 m. Waiting on LCM soaking time. |  | RIH back to bottom. Drill 12-1/4'' hole section as per directional plan. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | [5 empty] | Rig Down and Mobilization operations from WQ1-599 to WQ1-600. R/D %: 100, R/M %: 100, R/U: 68%. Expected Spud date 10th January-2026. |  | Continue Rig Up operations on WQ1-600. | 2026-01-06 | 2026-01-05
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | Continued increasing MW to 9.2 ppg. Continued preparing EZSqueeze LCM. Spotted EZSqueeze while SOOH to 9-5/8" casing shoe. Performed hesitation squeeze. Changed out RCD BA. RBIH to 1543m. |  | Spot LCM while strip OOH to 9-5/8" shoe. Retrieve RCD BA. POOH and L/D 8-1/2" RSS BHA. Jet WH, BOP and RCD. Install RCD PS. RIH 7" casing. | 2026-01-06 | 2026-01-05