## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | Drilled 12.1/4" hole section from 930 m to 1196 m. Pumped water and hi-vis pills. Drilled 12.1/4" hole section from 1196 m to 1779 m. |  | Drill 12.1/4" hole section to TD as per program. Circulate to clean hole. Perform wiper trip to 13.3/8" casing shoe. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | POOH 12 1/4" BHA with backreaming 13 3/8" casing shoe recording SONIC, RIH back to bottom for wiper trip, CHC & POOH & L/D 12 1/4" BHA to 100m. |  | L/D 12 1/4" BHA,#3, Perform WL logging Run #1, retrieve WB & jet wellhead, M/U & RIH 9 5/8" casing. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-613 | WQ-613 | Development | Onshore | 2025-12-03 |  |  |  |  | Displaced cased hole with 1 SG inhibited water, POOH 6-1/8" Directional BHA from 2884 m to 98 m and L/D 4" DP single by single (207 of 207 joints). POOH 6-1/8" Directional BHA to surface and L/D same, R/U WL tools. RIH 7" liner cement evaluation logging tool string. |  | Perform 7" casing cement evaluation log operations, POOH WL tools string to surface. RIH Polish Mill assembly on 5.5 DP to 1748 m. Dressed TOL and inside TBR. Displaced the well with 1.0 SG Inhibited Water. POOH Polish BHA to the surface and L/D same. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | RIH 6-1/8'' BHA to 2795 m. Conducted 9-5/8'' casing pressure test. Drilled shoe track + rat hole to 2807 m. Drilled 6-1/8" lateral hole section as per directional plan from 2807 m to 3215 m, No downhole losses. Performed a short trip for pipe Management to 2782 m. |  | Drill 6-1/8" lateral hole section as per directional plan. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | Circulated the hole clean, POOH 8-1/2" logging BHA to surface and L/D the same. P/U and M/U 8 1/2" pressure points logging BHA and RIH to 500 m, Performed shallow test-ok, RIH 8-1/2" pressure point logging BHA to 2637 m with no DHL. |  | Circulate hole clean, preform record pressure point in reservoir targets (20 points), RIH back to bottom, circulate hole clean, POOH 8-1/2" pressure point logging BHA to surface and L/D the same, perform formation evaluation log through TLC for open hole as per program. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Waited on LCM soaking time, RIH back by washing down to bottom at 1365 m. Drilled 12-1/4'' hole section as per directional plan to 1690 m, no downhole losses. |  | Drill 12-1/4'' hole section to one stand before Hartha FM. Circulate for hole clean. Drill 12-1/4'' hole section to section TD. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | [5 empty] | Rig Down and Mobilization operations from WQ1-599 to WQ1-600. R/D %: 100, R/M %: 100, R/U: 75%. Expected Spud date 10th January-2026. |  | Continue Rig Up operations on WQ1-600. | 2026-01-07 | 2026-01-06
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | Washed down from 1543m to bottom at 1751m. Circulated hole clean & increased MW to 9.5 ppg SBM. Stripped OOH 8-1/2" BHA from 1750m to 508m (spotted LCM pills at each depleted zone while stripping OOH). Retrieved RCD BA. POOH & L/D 8-1/2" BHA. Retrieved WB. Jetted clean WH & BOP with Tornar tool. Installed RCD PS. |  | Continue RIH 7" casing and land hanger at 1748m (shoe depth). Perform 7" casing cement job. P/test casing. Jetted clean packoff area. RIH and set 7" packoff. Perform full BOP test. M/U & RIH 6-1/8" RSS BHA. | 2026-01-07 | 2026-01-06