## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | RIH 9.5/8" casing from 767 m to 2500,6 m. R/U cement head and lines. P/T lines. Circulated prior to cementing job. |  | L/D landing joint. Wash BOP-WH. Install and P/T pack off. L/D 8" DC from mast. BOP P/T. Install wear bushing. M/U and RIH BHA #4 with 8.1/2" drill bit. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | Perform WL logging Run 2A, R/D logging tools, retreive WB, Jet wellhead, R/U WFD TRS equipment, M/U & RIH 7"x7 5/8" casing to 1175m. |  | RIH 7" x 7 5/8" Csg to BTM, CHC,Perform cement job & P/T casing at 4000 Psi, L/D landing jnt, jet WH & BOP, Install & test 7 5/8'' Pack-off, Change saver sub, P/U & RIH 6'' BHA. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-623 | WQ-623 | Development | Onshore | [5 empty] | Continued rigging down operations at WQ1-613, Rig R/D: 10 %; R/M %: 10%, R/U % : 02%. |  | Continue rigging down operations. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | R/U Wire Line equipment. Performed Cement evaluation log. Observed obstruction at 2720 m. Couldn't pass decided to POOH to surface. L/D WL Tools. P/U, M/U, and RIH 6" clean out BHA w/ 7" casing scraper to 2660 m. |  | Ream down from 2660 m to 2803 m. Circulate for hole cleaning. POOH to surface. Perform Cement evaluation log. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | Performed formation Evaluation job on Wireline for 8-1/2" open hole as per program. R/D WL tools and equipment, R/U liner running equipment. RIH 7" liner (26 ppf, L-80, VAM TOP HC) to 645 m. |  | RIH 7" liner (26 ppf, L-80, VAM TOP HC) to 787 m. P/U, M/U, and RIH 7" X 9-5/8" Liner Hanger Assembly, RIH 7" liner as per tally, Circulating Hole Clean, performing 7" Liner Cementing job as per program. POOH Liner Running Tools. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Installed Flowline. P/T 13-5/8'' BOP, OK. P/U, MU & RIH 8-1/2" clean out BHA to 1829 m. Drilled out DV and closing plug. RIH to 2071 m. Drilled out cement to 2114 m. Circulated for hole clean. Performed short trip: POOH 8-12'' clean out BHA from 2114 m to 1807 m, RIH back to bottom. Circulated for hole clean. Displaced the hole to 1.22 sg fresh mud. |  | POOH 8-1/2'' clean out BHA to surface. Perform 9-5/8'' cement evaluation wireline job. P/U & M/U & RIH 8-1/2'' directional BHA. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | 2026-01-09 |  |  |  |  | Drilling 17-1/2" wellbore through L.Fars , Ghar and Dammam formations to 958 m MD section TD, circulated hole clean, performed wiper trip to 84 m and RIH to 390 m. |  | RIH 17-1/2" DIR BHA to 958 m, circulate hole clean and spot Hi-Vis pill to cover Ghar interval, POOH 17-1/2'' DIR BHA to surface & L/D 17-1/2" BHA. N/D flow line and L/D conductor riser. R/U 13-3/8'' Casing running tools, P/U, M/U & RIH 13-3/8'' casing 54.5 ppf. BTC, L80 as per tally. | 2026-01-12 | 2026-01-11
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | C/O o-ring seal of C-pump. Troubleshot problem on batch mixer agitator & faulty cement unit 6x5 centrifugal pump. Performed dummy cement job. Pumped 9.1 ppg lo-vis SBM and cement spacer. Performed 7" casing cement job. P/tested 7" casing. L/D 7" csg hanger RT. R/D CRTi & 7" csg handling equipment. RIH RCD PS retrieving tool. |  | Unstabbed used BA and L/D 4" BART. Perform full BOP test. Set WB. M/U & RIH 6-1/8" RSS BHA. Drill out shoe track & 3m new formation. Perform LOT. Drill 6-1/8" hole to planned TD at +/-2600m. | 2026-01-12 | 2026-01-11