## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | Performed cementing job. R/D cement equipment. R/D CRT. L/D landing joint. Washed BOP-WH. Install and P/T pack off. L/D 8" DC from mast. BOP P/T. |  | RIH BHA #4 with 8.1/2" bit to tag TOC. Drill out float collar and cement. Displace to HOBM and drill out shoe. | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | RIH 7" x 7 5/8" Csg to 9 5/8" casg shoe, Circulate bottom up, continue RIH 7"x 7 5/8" csg to bottom, space out , R/U cmt head , ciruclation lowering YP to 10, Started 7"x7 5/8" Cement job. |  | Cement 7"csg & P/T, install & test 7 5/8'' Pack-off.RIH 6'' BHA, displace hole to 11.0 ppg ROBM, D/O shoe track and 3m formation, CHC, FIT to 14.0 ppg EMW,Drill 6" section (TD @ ~3130m) | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-623 | WQ-623 | Development | Onshore | [5 empty] | Continued rigging down operations at WQ1-613, Rig R/D: 20 %; R/M %: 35%, R/U % : 08%. |  | Continue rigging down and mobilization operations. | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | Reamed down from 2660 m to 2803 m. Circulated for hole cleaning. POOH to surface. R/U WL tools. RIH WL cement evaluation log to 2000m. Record short pass. Observed minor noise in IBC. POOH WL cement evaluation log to surface. Troubleshooting the IBC. RIH WL cement evaluation log to 2777m. Performed WL cement evaluation log for missed interval. POOH to surface. |  | R/D WL. RIH 5-5/8" Polish Mill assembly to 1710 m. Dress TOL and inside TBR. Displace the well with 1.0 SG Inhibited Water. POOH Polish BHA to surface. | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | RIH 7" liner (26 ppf, L-80, VAM TOP HC) to 787 m. P/U, M/U, and RIH 7" X 9-5/8" Liner Hanger Assembly, RIH 7" liner as per tally to 2635 m, Circulated hole clean. Set LH as per liner engineer. Continued circulating. Performed 7"liner cement job. Sting out setting tool, Circulated hole clean. |  | POOH Liner Running Tools, Perform pipe management with 4" HWDP and DP rack back stand to derrick, RIH 6-1/8'' clean out BHA with 7'' scrapers. RIH to tag cement. Drill out Cement. Set top packer and dressed off 7" TOL. Circulate hole clean. POOH 6-1/8" clean out BHA w/ 7" casing scraper to surface. | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | POOH 8-1/2'' clean out BHA to surface and lay down same. R/U WL tools. Performed 9-5/8'' cement evaluation log, observed noise in IBC reading, serviced the tool. Performed 9-5/8'' cement evaluation relog. |  | Continue performing 9-5/8'' cement evaluation wireline job. P/U & M/U & RIH 8-1/2'' directional BHA. Perform 9-5/8'' CSG PT. Drill out shoe track, rat hole and 3 m of new formation to 2129 m. Perform FIT. Drill 8-1/2'' section as per directional plan. | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | 2026-01-09 |  |  |  |  | Performed wiper trip with 17-1/2'' Dir BHA to 958 M section TD, POOH to surface and Lay Down 17-1/2'' DIR BHA, L/D RISER and RF Handling tools. R/U NE equipment to run 13-3/8" CSG 54.5#, L-80, Vam Top. P/U, M/U & RIH 13-3/8" CSG to 690 m. |  | RIH13-3/8" CSG 54.5#, L-80, Vam Top as per tally to the casing setting depth at 956 m, circulate hole clean, R/U cement head and lines. Cement 13-3/8" CSG. N/U 13-5/8" x 10 k BOP stack. P/T BOP. P/U, M/U and RIH with 12-1/4'' directional BHA. | 2026-01-13 | 2026-01-12
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | Jetted clean BOP with Tornar tool. Jetted clean packoff sealing area with Omni jetting tool. RIH packoff & attempted to pressure test seal, no success. Troubleshot problem, no success. Decision made to N/D BOP to inspect 7” csg hanger. P/test annulus. N/D diverter and overshot. R/U BOP secondary retention slings. |  | Set packoff and P/test seal. Perform full BOP test. N/U overshot and diverter. Set WB. M/U & RIH 6-1/8" RSS BHA. Drill out shoe track & 3m new formation. Perform LOT. Drill 6-1/8" hole to planned TD at +/-2600m. | 2026-01-13 | 2026-01-12