## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | Finished BOP P/T. Installed wear bushing. M/U and RIH BHA #4 to 2468 m (TOC). Drilled out cement to 2498 m. Displaced to HOBM. |  | Drill 8.1/2" hole section as per program. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | Perform cement job & P/T casing at 4000 Psi, jet WH & BOP, Install & test 7 5/8'' Pack-off, Change saver sub, P/U & RIH 6'' BHA., displaced to 11.0 ppg ROBM, Clean out shoe track, WOC. |  | C/O shoe track & 3 m new formation to 2875m, CHC, FIT @ 14.0ppg EMW, Drill 6" section to TD ~3130m , CHC & POOH 6" BHA#5. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-623 | WQ-623 | Development | Onshore | [5 empty] | Continued rigging down operations at WQ1-613, Rig R/D: 50 %; R/M %: 46%, R/U % : 15%. |  | Continue rigging down and mobilization operations. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | R/D WL. RIH 5-5/8" Polish Mill assembly to 1710 m. Dressed TOL and inside TBR. Displaced the well with 1.0 SG Inhibited Water. POOH Polish BHA to surface and L/D same. Retrieved Wear bushing. M/U jetting tool and flushed the well head. Performed TBG HGR Dummy Run. P/U, M/U and RIH 7" TBSA on 7" tubing Vam Top casing to 884 m. |  | P/U, M/U, and RIH 7" Upper completion assembly to 1710 m. Sting in and spaced-out tie back assembly. P/U and M/U 11'' TBG hanger on 4.5'' TBG joint and land in WH. P/T hanger seals and tieback seal assembly. N/D 13-5/8" BOP stack. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | POOH Liner Running Tools, Performed pipe management with 4" HWDP and DP rack back stand to derrick, M/U 6-1/8'' clean out BHA with 7'' scrapers to 110 m and the string dropped to hole, HPJSM, RIH 4" open end DP stand from surface to 2355 m. |  | RIH 4" open end DP stand to 2400 m (expected TOF) and engage fish by screw in 4" DP with TOF 4" tool joint, POOH with 6" clean out BHA to surface and L/D the same, perform pipe management with 4" DP rack back stand to derrick, RIH 6-1/8'' clean out BHA with 7'' scrapers. RIH to tag cement. Drill out Cement. Set top packer and dressed off 7" TOL. Circulate hole clean. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 16 | PIEP | HH-030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Performed 9-5/8'' cement evaluation wireline job. P/U & M/U & RIH 8-1/2'' directional BHA to 2114 m. Performed 9-5/8'' CSG PT, OK. Drilled out shoe track, rat hole and 3 m of new formation to 2129 m. Performed FIT, OK. Drilled 8-1/2'' section as per directional plan to 2174 m. |  | Drill 8-1/2'' section as per directional plan. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 16 | PIEP | HH-031 | WQ-600 | WQ-600 | Development | Onshore | 2026-01-09 |  |  |  |  | RIH13-3/8" CSG 54.5#, L-80, Vam Top as per tally to the casing setting depth at 956 m, circulated hole clean, waited on cementing service. R/U cement head and lines. Cemented 13-3/8" CSG. P/T casing. R/D cement head and lines. R/D NE CRT. N/U 13-5/8" x 10 k BOP stack. |  | N/U 13-5/8" x 10 k BOP stack. P/T BOP. P/U, M/U and RIH with 12-1/4'' directional BHA, Drill out cement and shoe track. Drill 12-1/4'' hole section as per directional plan. | 2026-01-14 | 2026-01-13
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | N/D BOP and lifted up BOP/riser. Inspect 7" csg hanger, found medium hard cement patches & debris in between 7" hanger neck & WH profile, clean cement & debris. N/U BOP/riser on WH. Set & P/test packoff seal. Performed full BOP test. N/U overshot & diverter. Set WB. M/U & RIH 6-1/8" RSS BHA & tagged top of wiper plug at 1715m. |  | Circulated hole clean prior to LOT. Perform LOT. Drill 6-1/8" hole to planned TD at 2600 m. | 2026-01-14 | 2026-01-13