## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | Displaced to HOBM. Drilled out casing shoe. Drilled to 2505 m and performed FIT. Drilled 8.1/2" hole to 2913 m. |  | Drill 8.1/2" hole section as per program. Wiper trip. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | Perform cement job & P/T casing at 4000 Psi, jet WH & BOP, Install & test 7 5/8'' Pack-off, Change saver sub, P/U & RIH 6'' BHA., displaced to 11.0 ppg ROBM, Clean out shoe track, WOC. |  | C/O shoe track & 3 m new formation to 2875m, CHC, FIT @ 14.0ppg EMW, Drill 6" section to TD ~3130m , CHC & POOH 6" BHA#5. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-623 | WQ-623 | Development | Onshore | [5 empty] | Continued rigging down operations at WQ1-613. R/D: 52 %; R/M %: 55%, R/U % : 18%. |  | Continue rigging down and mobilization operations. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-616 | WQ-616 | Development | Onshore | 2025-12-14 |  |  |  |  | P/U, M/U, and RIH 4-1/2" Upper completion assembly to 1710 m. Sting in and spaced-out tie back assembly. P/U and M/U 11'' TBG hanger on 4-1/2'' TBG joint and land in WH. P/T hanger seals and tieback seal assembly. Suspended the operation due to high wind speed. N/D 13-5/8" BOP stack. P/T X-Mass tree. Rig released from WQ1-616 on 13th January 2026 at 20:00. |  | Skidding operation from WQ1-616 to WQ1-620. Prepare to spud the well WQ1-620. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-620 | WQ-620 | Development | Onshore | [5 empty] | PREPARED FOR SKIDDING OPERATION FROM WQ1-616 TO WQ1-620. |  | Skidding operation from WQ1-616 to WQ1-620. Prepare to spud the well WQ1-620. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | RIH 5.5" DP stand from 2355 m to 2396 m(TOF), recorded string parameters, engaged fish by screw in 4" DP with TOF 4" tool joint. POOH 5.5" and 4" DP with 6" clean out BHA to surface and L/D the same. P/U, M/U and RIH 6" Clean out BHA to 1599 m. |  | RIH 6'' Clean out BHA with 7'' scraper. RIH to tag cement. Drill out Cement to 2609 m (2 m above float collar). Set top packer and dressed off 7" TOL. Circulate hole clean, Perform short trip and RIH to bottom, circulate hole clean, displace the well with the new section 1.26 SG brine, POOH with clean out BHA to TOL at 1839 m, circulate hole clean, POOH 6'' clean out BHA to surface and L/D same. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 16 | PIEP | HH030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Drilled 8-1/2'' section as per directional plan from 2174 m to 2688 m, DHL: 8-10 m3/hr started from 2563 m. |  | Drill 8-1/2'' section as per directional plan. Circulate hole clean. Perform wiper trip to casing shoe. POOH 8-1/2'' Dir BHA to surface. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 16 | PIEP | HH031 | WQ-600 | WQ-600 | Development | Onshore | 2026-01-09 |  |  |  |  | N/U 13-5/8" x 10 k BOP stack. P/T BOP. Installed wear bushing, waited on weather, P/U, M/U & RIH 12-1/4" BHA to 460 m. performed well control drills, conduct shallow hole test, resume RIH 12-1/4" directional BHA to 672 m. |  | RIH with 12-1/4'' directional BHA, Drill out cement and shoe track. Drill 12-1/4'' hole section as per directional plan. | 2026-01-15 | 2026-01-14
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | Drilled out 3 x wiper plugs, FC, shoetrack and FS to 1751m. Cleaned out rathole and drilled 3m new formation to 1754m. Circulated hole clean. Performed LOT. Drilled 6-1/8" hole with PD RSS (Geosteering) BHA from 1754m to 1922m. |  | Drill 6-1/8" hole to planned TD at 2600 m. Circulate hole clean. POOH 6-1/8" RSS BHA to surface and L/D. | 2026-01-15 | 2026-01-14