## Sheet1
Flag | Region | Zone | APH | Rig Name | Well Name | Well Name_2 | Well Type | Location | Spud Date | Release Date | Status | Status Code [1] | Status Code [2] | Current Operation | Current Status | 24 hrs look ahead | Report Date | Operation Date
INC | Region 5 | Zone 15 | PIEP | ENAFOR 45 | QB-117 | QB-117 | Development | Onshore | 2025-12-28 |  |  |  |  | POOH and L/D BHA #4 from 240 m to surface. R/U SLB E-line logging and performed logging operation. |  | Recover wear bushing. Perform 7" casing dummy run. RIH 7" 29 ppf P110 VAM TOP casing with conventional TRS until 253 m. R/U CRT equipment. Continue RIH 7" 29 ppf P110 VAM TOP casing with CRT as per plan. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 15 | PIEP | ENAFOR 62 | EMK-81 | EMK-81 | Development | Onshore | 2025-12-30 |  |  |  |  | RU & RIH with SLB WL MDT-IFA-GR. Worked on stuck points at 2957m & 2973m. POOH & L/D WL tools.RIH 6" C/O assy.washed down to TD, CHC, POOH to 221m. |  | L/D Clean out BHA#6, R/U and RIH with SLB WL OH MDT logging tools. Perform logging program run 3C: MDT - IFA - GR (12 stations planned). | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 16 | PIEP | GW-165 | WQ-623 | WQ-623 | Development | Onshore | [5 empty] | Continued rigging down operations at WQ1-613. R/D: 100 %; Rig-R/M: 98%. Rig-R/U :28%. Camp- R/D:100 %; R/M: 100% ; R/U:85%. |  | Continue rigging down and mobilization operations. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 16 | PIEP | GW-166 | WQ-620 | WQ-620 | Development | Onshore | 2026-01-14 |  |  |  |  | POOH 17-1/2" BHA to surface and L/D the same. RIH 13-3/8" CSG to 784 m. Perform 13 3/8" CSG cement job. |  | L/D casing running equipment. N/U 13-5/8'' x 10 K BOP stack. Pressure test BOP. Installed wear bushing. P/U, M/U & RIH 12-1/4'' directional BHA. Drill out cement and shoe track. Drill 12-1/4" directional hole as per plan. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-615 | WQ-615 | Development | Onshore | 2025-11-22 |  |  |  |  | N/D 13-5/8" 10 K BOP stack. Landed T.HGR in THS, N/U THA + 4-1/16" 5K LMV. PT T.HGR and THA seals. Rig released at 09:00. |  | R/D and skid the rig to next well slot WQ1-617, R/U operations. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 16 | PIEP | GW-51 | WQ-617 | WQ-617 | Development | Onshore | [5 empty] | Skidded the rig 22 m to next well slot WQ1-617. Rig move and Rig operations at WQ1-617. Prepared rig to spud on WQ1-617. Installed conductor pipe raiser and secured same. |  | Make up 17-1/2" BHA as plan. Test surface lines. Complete Pre-spud check list. Spud well WQ1-617. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 16 | PIEP | HH030 | WQ-625 | WQ-625 | Development | Onshore | 2025-12-31 |  |  |  |  | Run 7'' liner as per tally to setting depth at 2769 m. Set liner hanger. Performed 7" liner cementing job. Stung out the hanger running tool and circulated out excess cement. POOH 7" liner running tool to surface. P/U, M/U RIH 6'' clean out BHA to 1322 m. |  | RIH 6'' clean out BHA to TOC. Drill out cement & shoe track to 12 m above the liner shoe. Circulate hole clean. Set Packer. Perform short trip. Circulate hole clean. POOH 6" clean out BHA to surface. Perform 7'' liner cement evaluation log. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 16 | PIEP | HH031 | WQ-600 | WQ-600 | Development | Onshore | 2026-01-09 |  |  |  |  | Drilled 12-1/4'' hole section through UER, Tayarat and Shiranish formations to 1879 m, circulated hole clean, performed flow check, POOH to change the 12-1/4" Bit from 1879 m to 385 m. |  | POOH 12-1/4'' DIR BHA to surface to change Bit, RIH 12-1/4" BHA to 1879 m, resume drilling 12-1/4" directional hole section as per plan. | 2026-01-18 | 2026-01-17
INC | Region 5 | Zone 17 | PIEP | NAGA-5 | SNPA-22 | SNPA-22 | Development | Offshore | 2025-12-26 |  |  |  |  | POOH 6-1/8" RSS BHA from 2336 to 1743m. Circulate hole clean. POOH 6-1/8" RSS BHA to surface and L/D. M/U and RIH 6-1/8" check trip BHA to 1650m. Reamed across planned completion packer setting depth interval and circulated BU. RIH 6-1/8" check trip BHA to 2380m. |  | POOH 6-1/8" check trip BHA to 7" shoe. CHC. RIH to bottom. CHC & displace open hole to 200m inside 7" shoe with 13.3 ppg PST DIF SBM. POOH to 100m inside 7" shoe. Circulate with 13.3 ppg PST DIF SBM to obtain 3xpasses of PST. POOH & R/B check trip. | 2026-01-18 | 2026-01-17