## Sheet1
Region | Asset | Rig Name | Well Name | Spud Date | Current Operation | 24 hrs look ahead
REGION 5 | ALGERIA | ENAFOR 45 | QB-117 | 2025-12-28 | Circulated to clean hole. POOH BHA #3 to 439 m. Circulated bottoms up, flow check. RIH BHA #3 to 2503 m. | Circulate to clean hole and drop gyro. POOH BHA #3 to surface. L/D stabilizers and drill bit. Run CH logs as per plan.
REGION 5 | ALGERIA | ENAFOR 62 | EMK-81 | 2025-12-30 | RIH 9 5/8" csg to bottom, R/U cmt head, CHC, perform 9 5/8" csg cement job, P/T csg, Set and test Pack off, install wear bushing, P/U & RIH 8-1/2" BHA #4. | RIH & Drill out shoe track & displace to 16.5 ppg mud, Drill 3m new formation, CHC, FIT at 19.5 ppg EMW, Drill 8 1/2'' hole to section TD ~2881m, CHC, POOH to 9 5/8" Csg shoe, FIT to 18.5 EMW.
REGION 5 | IRAQ | GW-165 | WQ-613 | 2025-12-03 | POOH 7.5" Polish mill assemble while L/D 5-1/2" DP single by single from 1746 m to surface and L/D same .Retrieved Wear bushing. M/U jetting tool and flushed the well head, Performed TBG HGR Dummy Run. P/U, M/U and RIH 7" TBSA on 7" lined Vam Top casing to 450m. | Continue RIH 7" TBSA on 7" Vam Top lined casing to 1748 m. Sting in and space-out tie back assembly. P/U and M/U 11'' TBG hanger on 7" Vam Top lined casing and land in THS. P/T hanger seals and tie-back seal assembly. N/D 13-5/8" BOP stack. N/U THA and X-Mass tree lower part and P/T the same. Release the rig.
REGION 5 | IRAQ | GW-51 | WQ-615 | 2025-11-22 | POOH 8-1/2" pressure point logging BHA to surface and L/D the same. R/U WL tools and equipment. RIH TLC WL open hole logging tools on 5-1/2"DP to 2111 m (latch depth). Circulated 1.5 string volume. | Perform formation evaluation log through TLC for open hole as per program, POOH WL FMI log on 5-1/2"DP (TLC) to Surface.
REGION 5 | IRAQ | GW-166 | WQ-616 | 2025-12-14 | Drilled 6-1/8" hole section from 3885 m to 4596 m. No downhole losses. | Drill 6-1/8" Lateral Hole Section to section TD as per directional plan. Circulate the hole. Perform Wiper trip to 2805 m. RIH back to bottom. Circulate for hole cleaning. Displace mud in the open hole with 1.05 SG brine. POOH 6-1/8" directional BHA to 7" liner shoe.
REGION 5 | IRAQ | HH-030 | WQ-625 | 2025-12-31 | Drilled 12-1/4'' hole section as per directional plan from 2003 m to 2126 m (Section TD). Circulated hole clean. POOH 12-1/4'' BHA to 1910 m (backreamed from 2047 m to 1943 m). RIH 12-1/4'' BHA to bottom. Circulated hole clean. POOH 12-1/4'' BHA free on elevator to 1135 m. Spotted LCM across Dammam FM. POOH 12-1/4'' BHA free on elevator to 13-3/8'' CSG shoe. | POOH 12-1/4'' BHA to surface. L/D same. R/U NE casing running tools. Run 9-5/8'' CSG.
REGION 5 | IRAQ | HH-031 | WQ-600 |  | Rig Down and Mobilization operations from WQ1-599 to WQ1-600. R/D %: 100, R/M %: 100, R/U: 90%. Expected Spud date 10th January-2026. | Continue Rig Up operations on WQ1-600.
REGION 5 | MALAYSIA | NAGA-5 | SNPA-22 | 2025-12-26 | Circulated out cement slurry until 9.5 ppg SBM return to surface. Flushed choke and kill lines, MPD line, boosting line, return line from SOV, BOP and wellhead with 9.5 ppg SBM. Continued circulate hole with 9.5 ppg SBM while waiting for replacement cement unit HPU. | Continue circulate hole while waiting for replacement cement unit HPU. C/O cement unit HPU and function test and R/U batch mixer as contingency. Perform 7" casing cement job.