## Sheet1
Region | Asset | Rig Name | Well Name | Spud Date | Current Operation | 24 hrs look ahead
REGION 5 | ALGERIA | ENAFOR 45 | QB-117 | 2025-12-28 | POOH BHA #3 to surface. Run CBL to 13.3/8" casing. Retrieved wear bushing. Washed BOP/WH. Performed dummy run with 9.5/8" csg hanger. R/U CRT. RIH 9.5/8" casing from surface to 767 m. | Continue RIH 9.5/8" casing. Circulate prior to cement job. Cement 9.5/8" casing as per program.
REGION 5 | ALGERIA | ENAFOR 62 | EMK-81 | 2025-12-30 | Drilled 8 1/2'' hole to section TD @ 2872m, CHC, POOH to 9 5/8" Csg shoe, FIT to 18.0 EMW, POOH L/D DP & BHH, RIH WL logging Run#2A. | Perform WL logging Run 2A, R/D logging tools, retreive WB, Jet wellhead, R/U WFD TRS equipment, M/U & RIH 7"x7 5/8" casing.
REGION 5 | IRAQ | HH-031 | WQ-600 | 2026-01-09 | Rig is accepted to spud in WQ1-600 on 09:00 am 09-Jan-2026. Drilled 17-1/2'' hole section in rotary and sliding mode from 68 m to 570 m. | Continue drilling 17-1/2" wellbore to section TD. POOH 17-1/2" DIR BHA to surface and lay down same.
REGION 5 | IRAQ | GW-165 | WQ-613 | 2025-12-03 | P/U and M/U 11'' TBG hanger on 7" Vam Top lined casing and land in THS. P/T hanger seals and tie-back seal assembly. N/D 13-5/8" BOP stack. N/U THA and X-Mass tree lower part and P/T the same. Release the rig on 9th Jan,2026. | -
REGION 5 | IRAQ | GW-51 | WQ-615 | 2025-11-22 | RIH run #1 dummy wireline with caliper log to bottom, and POOH to surface. Performed Run#2 FMI-SONIC log on wireline, POOH to surface and L/D the same, R/U and Perform Run#3 ECS-SGR log on wireline on going. | Perform formation Evaluation job on Wireline for 8-1/2" open hole as per program, R/U for running 7" liner. P/U, M/U and RIH 7" liner as per tally.
REGION 5 | IRAQ | GW-166 | WQ-616 | 2025-12-14 | RIH back to bottom. Circulated for hole cleaning. Displaced mud in the open hole with 1.05 SG brine. POOH 6-1/8" directional BHA to 2783 m. Displaced cased hole volume with 1.0 SG inhibited water. POOH 6-1/8" Directional BHA to surface and L/D same. R/U WL tools. Average Static losses 2 - 3 m3/hr. | Perform Cement evaluation log. RIH 5-5/8" Polish Mill assembly to 1710 m. Dress TOL and inside TBR. Displace the well with 1.0 SG Inhibited Water. POOH Polish BHA to surface.
REGION 5 | IRAQ | HH-030 | WQ-625 | 2025-12-31 | RIH 9-5/8" casing joints as per tally to setting depth at 2124 m. Circulated hole clean. R/U Cement Head. Performed 9-5/8'' cement job in first stage as per the program. Inflated Hall ICP packer and opened DV ports. Established circulation thru DV ports. Waited for cement meanwhile prepared mix fluid for 2nd stage. Performed 2nd stage cement job and top job. Lifted BOP stack. Set 9 5/8" casing slips. Cut 9-5/8'' CSG. N/D BOP. Installed WH Section and PT same, OK. N/U 13-5/8'' BOP stack. | Install Flowline. P/T 13-5/8'' BOP. P/U, MU & RIH 8-1/2" clean out BHA. Drill out cement above DV and closing plug. RIH and tag TOC for first stage. Drill out cement to 10 m above shoe depth. Circulate for hole clean. Perform short trip above first stage TOC. Circulate for hole clean. Displace hole with 1.22 sg fresh mud. POOH 8-1/2'' clean out BHA to surface.
REGION 5 | IRAQ | GW-165 | WQ-623 |  | Pre-move operation from Pad: LM-93.5 Well:WQ1-613 to Next location FJ-79.5 Well: WQ1-623. Working on disconnect mud system surface line and power cable. Disconnect MP HP line . B/O and L/D 44 stands from derrick on going. | Continue Rig Down and Mobilization operations LM-93.5 Well:WQ1-613 to Next location FJ-79.5 Well: WQ1-623.
REGION 5 | MALAYSIA | NAGA-5 | SNPA-22 | 2025-12-26 | R/U back up cement head and surface line. Continued circulate hole with 9.5ppg SBM. Spotted and R/U cement unit HPU and cement batch mixer. Function test both. Observed C-pump of batch mixer leaking. C/O o-ring seal inside C-pump meanwhile circulate hole with 9.5ppg SBM. | Perform dummy cement job. Pump 120% csg volume of 9.1 ppg SBM. Pump spacer. Perform 7" csg cement job. R/D cement head & L/D landing joints. Jet clean BOP with Tornar tool. Wash packoff area, set & test packoff. Perform full BOP test.