## Sheet1
Region | Asset | Rig Name | Well Name | Spud Date | Current Operation | 24 hrs look ahead
REGION 5 | ALGERIA | ENAFOR 45 | QB-117 | 2025-12-28 | Finished BOP P/T. Installed wear bushing. M/U and RIH BHA #4 to 2468 m (TOC). Drilled out cement to 2498 m. Displaced to HOBM. | Drill 8.1/2" hole section as per program.
REGION 5 | ALGERIA | ENAFOR 62 | EMK-81 | 2025-12-30 | Perform cement job & P/T casing at 4000 Psi, jet WH & BOP, Install & test 7 5/8'' Pack-off, Change saver sub, P/U & RIH 6'' BHA., displaced to 11.0 ppg ROBM, Clean out shoe track, WOC. | C/O shoe track & 3 m new formation to 2875m, CHC, FIT @ 14.0ppg EMW, Drill 6" section to TD ~3130m , CHC & POOH 6" BHA#5.
REGION 5 | IRAQ | HH-031 | WQ-600 | 2026-01-09 | RIH13-3/8" CSG 54.5#, L-80, Vam Top as per tally to the casing setting depth at 956 m, circulated hole clean, waited on cementing service. R/U cement head and lines. Cemented 13-3/8" CSG. P/T casing. R/D cement head and lines. R/D NE CRT. N/U 13-5/8" x 10 k BOP stack. | N/U 13-5/8" x 10 k BOP stack. P/T BOP. P/U, M/U and RIH with 12-1/4'' directional BHA, Drill out cement and shoe track. Drill 12-1/4'' hole section as per directional plan.
REGION 5 | IRAQ | GW-51 | WQ-615 | 2025-11-22 | POOH Liner Running Tools, Performed pipe management with 4" HWDP and DP rack back stand to derrick, M/U 6-1/8'' clean out BHA with 7'' scrapers to 110 m and the string dropped to hole, HPJSM, RIH 4" open end DP stand from surface to 2355 m. | RIH 4" open end DP stand to 2400 m (expected TOF) and engage fish by screw in 4" DP with TOF 4" tool joint, POOH with 6" clean out BHA to surface and L/D the same, perform pipe management with 4" DP rack back stand to derrick, RIH 6-1/8'' clean out BHA with 7'' scrapers. RIH to tag cement. Drill out Cement. Set top packer and dressed off 7" TOL. Circulate hole clean.
REGION 5 | IRAQ | GW-166 | WQ-616 | 2025-12-14 | R/D WL. RIH 5-5/8" Polish Mill assembly to 1710 m. Dressed TOL and inside TBR. Displaced the well with 1.0 SG Inhibited Water. POOH Polish BHA to surface and L/D same. Retrieved Wear bushing. M/U jetting tool and flushed the well head. Performed TBG HGR Dummy Run. P/U, M/U and RIH 7" TBSA on 7" tubing Vam Top casing to 884 m. | P/U, M/U, and RIH 7" Upper completion assembly to 1710 m. Sting in and spaced-out tie back assembly. P/U and M/U 11'' TBG hanger on 4.5'' TBG joint and land in WH. P/T hanger seals and tieback seal assembly. N/D 13-5/8" BOP stack.
REGION 5 | IRAQ | HH-030 | WQ-625 | 2025-12-31 | Performed 9-5/8'' cement evaluation wireline job. P/U & M/U & RIH 8-1/2'' directional BHA to 2114 m. Performed 9-5/8'' CSG PT, OK. Drilled out shoe track, rat hole and 3 m of new formation to 2129 m. Performed FIT, OK. Drilled 8-1/2'' section as per directional plan to 2174 m. | Drill 8-1/2'' section as per directional plan.
REGION 5 | IRAQ | GW-165 | WQ-623 |  | Continued rigging down operations at WQ1-613, Rig R/D: 50 %; R/M %: 46%, R/U % : 15%. | Continue rigging down and mobilization operations.
REGION 5 | MALAYSIA | NAGA-5 | SNPA-22 | 2025-12-26 | N/D BOP and lifted up BOP/riser. Inspect 7" csg hanger, found medium hard cement patches & debris in between 7" hanger neck & WH profile, clean cement & debris. N/U BOP/riser on WH. Set & P/test packoff seal. Performed full BOP test. N/U overshot & diverter. Set WB. M/U & RIH 6-1/8" RSS BHA & tagged top of wiper plug at 1715m. | Circulated hole clean prior to LOT. Perform LOT. Drill 6-1/8" hole to planned TD at 2600 m.